## Buildout Pipeline
Modo Energy Battery Pipeline - May 2024 - December 2031
Site Name | Interconnecting Entity | Power (MW) | ERCOT Projected Commercial Operations Month | Modo Projected Commercial Operations Month | County | CDR Reporting Zone | Interconnection Study Phase
Big Star Storage | RWE Solar Development, LLC | 80 | 2024-04-01 | 2024-05-01 | Bastrop | SOUTH | SS Completed, FIS Completed, IA
Myrtle Storage | Myrtle Storage, LLC | 151.2 | 2024-05-01 | 2024-05-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
Coral Storage | Copperhead Solar, LLC | 99 | 2024-06-01 | 2024-06-01 | Falls | NORTH | SS Completed, FIS Completed, IA
Bright Arrow Storage | RWE Solar Development, LLC | 103.56 | 2024-06-01 | 2024-06-01 | Hopkins | NORTH | SS Completed, FIS Completed, IA
Fence Post BESS | Fence Post Solar Project, LLC | 72.23 | 2024-05-01 | 2024-07-01 | Navarro | NORTH | SS Completed, FIS Completed, IA
Stampede BESS | Stampede Solar Project, LLC | 72.38 | 2024-05-01 | 2024-07-01 | Hopkins | NORTH | SS Completed, FIS Completed, IA
Dickens BESS | BRP INTERMEDIATECO I LLC | 200.8 | 2024-05-01 | 2025-02-01 | Dickens | PANHANDLE | SS Completed, FIS Completed, IA
Rodeo Ranch Energy Storage Repowering | Rodeo Ranch Energy Storage, LLC | 10 | 2024-05-01 | 2024-08-01 | Reeves | WEST | SS Completed, FIS Completed, IA
Danish Fields Storage | Danish Fields Storage, LLC | 152.43 | 2024-04-01 | 2024-08-01 | Wharton | SOUTH | SS Completed, FIS Completed, IA
Giga Texas Energy Storage | Giga Texas Energy, LLC. | 131.05 | 2024-04-01 | 2024-08-01 | Travis | SOUTH | SS Completed, FIS Completed, IA
Five Wells BESS | Five Wells Storage LLC | 220.8 | 2024-04-01 | 2024-08-01 | Bell | NORTH | SS Completed, FIS Completed, IA
Callisto I Energy Center | Callisto I energy center LLC | 206.4 | 2024-06-01 | 2024-09-01 | Harris | HOUSTON | SS Completed, FIS Completed, IA
Pavo BESS | BRP Pavo BESS LLC | 175.8 | 2024-06-01 | 2024-09-01 | Pecos | WEST | SS Completed, FIS Completed, IA
BoCo BESS | BoCo BESS | 155.48 | 2024-06-01 | 2024-09-01 | Borden | WEST | SS Completed, FIS Completed, IA
Ebony Energy Storage | Ebony Energy Storage, LLC | 203.5 | 2024-06-01 | 2024-09-01 | Comal | SOUTH | SS Completed, FIS Completed, IA
Anemoi Energy Storage | Anemoi Energy Storage, LLC | 205 | 2024-06-01 | 2024-09-01 | Hidalgo | SOUTH | SS Completed, FIS Completed, IA
GULF STAR STORAGE | GulfStar Power, LLC | 305.48 | 2024-06-01 | 2024-09-01 | Wharton | SOUTH | SS Completed, FIS Completed, IA
Angelo Storage | Angelo Storage, LLC | 102.97 | 2024-05-01 | 2024-10-01 | Tom Green | WEST | SS Completed, FIS Completed, IA
Hydra BESS | BRP Hydra BESS LLC | 200.8 | 2024-07-01 | 2024-10-01 | Pecos | WEST | SS Completed, FIS Completed, IA
Tortolas BESS | BRP Tortolas BESS LLC | 50.3 | 2024-07-01 | 2024-10-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
Sheep Creek Storage | Longhorn Storage LLC | 142.1 | 2024-07-01 | 2024-10-01 | Callahan | WEST | SS Completed, FIS Completed, IA
Hummingbird Storage | KCE TX 10, LLC | 103.8 | 2024-07-01 | 2024-10-01 | Denton | NORTH | SS Completed, FIS Completed, IA
Limousin Oak Storage | KCE TX 15, LLC | 104.62 | 2024-07-01 | 2024-10-01 | Grimes | NORTH | SS Completed, FIS Completed, IA
River Bend | Brazos Bend BESS LLC | 101.64 | 2024-07-01 | 2024-10-01 | Fort Bend | HOUSTON | SS Completed, FIS Completed, IA
Paleo BESS | BRP Paleo BESS LLC | 200.8 | 2024-07-01 | 2024-10-01 | Hale | PANHANDLE | SS Completed, FIS Completed, IA
Estonian Storage | Enel Green Power Estonian Solar Project, LLC | 101.6 | 2024-09-01 | 2024-10-01 | Delta | NORTH | SS Completed, FIS Completed, IA
Connolly Storage | BT Connolly Storage, LLC | 125.36 | 2024-08-01 | 2024-11-01 | Wise | NORTH | SS Completed, FIS Completed, IA
Al Pastor BESS | Al Pastor BESS LLC | 103.1 | 2024-08-01 | 2024-11-01 | Dawson | WEST | SS Completed, FIS Completed, IA
Wigeon Whistle BESS | Wigeon Whistle BESS | 122.9 | 2024-09-01 | 2024-12-01 | Collin | NORTH | SS Completed, FIS Completed, IA
Great Kiskadee Storage | Great Kiskadee Storage, LLC | 103.05 | 2024-09-01 | 2024-12-01 | Hidalgo | SOUTH | SS Completed, FIS Completed, IA
Holy ESS | Citadel BESS LLC | 209.32 | 2024-09-01 | 2024-12-01 | Harris | HOUSTON | SS Completed, FIS Completed, IA
Eliza Storage | Ables Springs Storage, LLC | 100.4 | 2024-09-01 | 2024-12-01 | Kaufman | NORTH | SS Completed, FIS Completed, IA
Jade Storage SLF | IP Renewable Energy Holdings LLC | 0 | 2024-09-01 | 2024-12-01 | Scurry | WEST | SS Completed, FIS Completed, IA
Ryan Energy Storage | Ryan Storage LLC | 50 | 2024-10-01 | 2025-01-01 | Coryell | NORTH | SS Completed, FIS Completed, IA
Inertia BESS | Inertia Energy Storage, LLC | 13 | 2024-10-01 | 2025-01-01 | Haskell | WEST | SS Completed, FIS Completed, IA
Longbow BESS | Longbow BESS, LLC | 180.8 | 2024-11-01 | 2025-02-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
Carina BESS | BRP Carina BESS LLC | 154.11 | 2024-12-01 | 2025-03-01 | Nueces | COASTAL | SS Completed, FIS Completed, IA
Padua Grid BESS | Padua Grid, LLC | 51.1 | 2024-12-01 | 2025-03-01 | Bexar | SOUTH | SS Completed, FIS Completed, IA
Crowned Heron BESS | RWE Renewables | 150 | 2024-12-01 | 2025-03-01 | Fort Bend | HOUSTON | SS Completed, FIS Completed, IA
Tanzanite Storage | Tanzanite Energy Storage LLC | 265.8 | 2024-12-01 | 2025-03-01 | Henderson | NORTH | SS Completed, FIS Completed, IA
SOHO BESS | ESTX-PLDHOUSTON2 | 206.32 | 2025-01-01 | 2025-04-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
SOHO II BESS | Black Mountain Energy Storage II | 206.32 | 2025-01-01 | 2025-04-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
Ironman BESS | SMT Ironman BESS LLC | 308.4 | 2025-01-01 | 2025-04-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
Lower Rio BESS | VESI 38 LLC | 60.45 | 2025-01-01 | 2025-04-01 | Hidalgo | SOUTH | SS Completed, FIS Completed, IA
Burksol BESS | Donegal BESS | 103.27 | 2025-01-01 | 2025-04-01 | Dickens | PANHANDLE | SS Completed, FIS Completed, IA
Desert Willow BESS | Desert Willow Energy Storage, LLC | 154.4 | 2025-02-01 | 2025-05-01 | Ellis | NORTH | SS Completed, FIS Completed, IA
Anole BESS | Anole Energy Storage, LLC | 247.1 | 2025-02-01 | 2025-05-01 | Dallas | NORTH | SS Completed, FIS Completed, IA
Angels Creek | Angels Creek LLC | 31.68 | 2024-06-01 | 2025-06-01 | Webb | SOUTH | SS Completed, FIS Completed, No IA
BRP Mensa BESS | BRP Mensa BESS LLC | 404.99 | 2024-06-01 | 2025-06-01 | Pecos | WEST | SS Completed, FIS Started, No IA
BRP Bonete BESS | BRP Bonete BESS LLC | 201.13 | 2024-06-01 | 2025-06-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Marcelina Storage | Marcelina Solar, LLC | 203.21 | 2024-06-01 | 2025-06-01 | Wilson | SOUTH | SS Completed, FIS Started, No IA
Dogfish BESS | Dogfish ESS Assets, LLC | 75 | 2025-04-01 | 2025-07-01 | Pecos | WEST | SS Completed, FIS Completed, IA
Orange Grove BESS | Talitha Energy Project, LLC | 61.39 | 2025-04-01 | 2025-07-01 | Jim Wells | SOUTH | SS Completed, FIS Completed, IA
Trojan BESS | Trojan BESS | 201.9 | 2024-08-01 | 2025-08-01 | Cooke | NORTH | SS Completed, FIS Started, No IA
Hickerson BESS | Hickerson BESS | 302.4 | 2024-08-01 | 2025-08-01 | Bosque | NORTH | SS Completed, FIS Started, No IA
Camp Creek Storage SLF | White Rock Solar | 0 | 2024-08-01 | 2025-08-01 | Robertson | NORTH | SS Completed, FIS Completed, IA
Chillingham Storage | Chillingham Solar LLC | 153.93 | 2025-05-01 | 2025-08-01 | Bell | NORTH | SS Completed, FIS Completed, IA
Walstrom BESS | Sealy Power LLC | 200 | 2025-05-01 | 2025-08-01 | Austin | SOUTH | SS Completed, FIS Completed, IA
Lucky Bluff BESS | Lucky Bluff BESS LLC | 100.8 | 2025-05-01 | 2025-08-01 | Erath | NORTH | SS Completed, FIS Completed, IA
Black Springs BESS | Black Springs BESS LLC | 120.96 | 2025-05-01 | 2025-08-01 | Palo Pinto | NORTH | SS Completed, FIS Completed, IA
Old Aqueduct Batt | Old Aqueduct LLC | 302.94 | 2024-09-01 | 2025-09-01 | Hale | PANHANDLE | SS Completed, FIS Completed, No IA
Andromeda Storage SLF | IP Lumina II BESS, LLC | 0 | 2024-09-01 | 2025-09-01 | Scurry | WEST | SS Completed, FIS Started, IA
Coneflower Storage Project | Coneflower Storage Project LLC | 170 | 2025-06-01 | 2025-09-01 | Chambers | HOUSTON | SS Completed, FIS Completed, IA
Bocanova BESS | Bocanova Power LLC | 300.92 | 2025-06-01 | 2025-09-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
Headcamp | Headcamp BESS | 150 | 2025-06-01 | 2025-09-01 | Pecos | WEST | SS Completed, FIS Completed, IA
Stockyard Grid Batt | Stockyard Grid, LLC | 150.6 | 2025-06-01 | 2025-09-01 | Tarrant | NORTH | SS Completed, FIS Completed, IA
SP Jaguar BESS | SP-Jaguar Solar LLC | 300 | 2025-06-01 | 2025-09-01 | McLennan | NORTH | SS Completed, FIS Completed, IA
Pradera Storage | Pradera Storage, LLC | 153.11 | 2024-10-01 | 2025-10-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
Cottonwood Bayou Storage | Cottonwood Bayou Storage, LLC | 153.03 | 2025-07-01 | 2025-10-01 | Brazoria | COASTAL | SS Completed, FIS Completed, IA
Guajillo Energy Storage | Guajillo Energy Storage LLC | 204.8 | 2025-07-01 | 2025-10-01 | Webb | SOUTH | SS Completed, FIS Completed, IA
Cartwheel BESS 1 | Cartwheel BESS, LLC | 156.91 | 2025-07-01 | 2025-10-01 | Hopkins | NORTH | SS Completed, FIS Completed, IA
Montezuma Storage | Montezuma Storage LLC | 50.6 | 2024-11-01 | 2025-11-01 | Colorado | SOUTH | SS Completed, FIS Completed, No IA
Volunteer Storage | Blackjack Storage LLC | 50.6 | 2024-11-01 | 2025-11-01 | Caldwell | SOUTH | SS Completed, FIS Started, No IA
Chariot Storage | Chariot Storage LLC | 50 | 2024-11-01 | 2025-11-01 | Limestone | NORTH | SS Completed, FIS Started, No IA
Edgewater Storage | Edgewater Battery Storage LLC | 50 | 2024-11-01 | 2025-11-01 | Ellis | NORTH | SS Completed, FIS Started, No IA
BRP Kotys BESS | BRP Kotys BESS LLC | 163.41 | 2024-11-01 | 2025-11-01 | Denton | NORTH | SS Completed, FIS Started, No IA
Leighton BESS SLF | Lavender Solar LLC | 0 | 2024-11-01 | 2025-11-01 | Limestone | NORTH | SS Completed, FIS Started, No IA
Ebony Energy Storage Repowering | Ebony Energy Storage, LLC | 5 | 2024-11-01 | 2025-11-01 | Comal | SOUTH | SS Completed, FIS Started, No IA
Anemoi Energy Storage Repowering | Anemoi Energy Storage, LLC | 5 | 2024-11-01 | 2025-11-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Starling Storage | Starling Storage, LLC | 63.6 | 2024-11-01 | 2025-11-01 | Gonzales | SOUTH | SS Completed, FIS Completed, No IA
XE Hermes Storage | Bell Solar 1 LLC | 100.42 | 2025-08-01 | 2025-11-01 | Bell | NORTH | SS Completed, FIS Completed, IA
Antlia BESS | BRP Antlia BESS LLC | 72.38 | 2024-12-01 | 2025-12-01 | Val Verde | WEST | SS Completed, FIS Started, IA
BRP Musca BESS | BRP Musca BESS LLC | 100.51 | 2024-12-01 | 2025-12-01 | Reagan | WEST | SS Completed, FIS Started, No IA
Cachi BESS | BRP Cachi BESS LLC | 205.46 | 2024-12-01 | 2025-12-01 | Guadalupe | SOUTH | SS Completed, FIS Started, IA
BRP Perseus BESS | BRP Perseus BESS LLC | 202.5 | 2024-12-01 | 2025-12-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
SPC Bloom BESS | BRP Blue Topaz 2, LLC | 100 | 2024-12-01 | 2025-12-01 | Victoria | SOUTH | SS Completed, FIS Started, No IA
BRP Volans BESS | BRP Volans BESS LLC | 206.88 | 2024-12-01 | 2025-12-01 | Winkler | WEST | SS Completed, FIS Completed, No IA
BRP Galan BESS | BRP Galan BESS LLC | 75.97 | 2024-12-01 | 2025-12-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
BRP Ampato BESS | BRP Ampato BESS LLC | 121.56 | 2024-12-01 | 2025-12-01 | Crane | WEST | SS Completed, FIS Started, No IA
BRP Pobeda BESS | BRP Pobeda BESS LLC | 301.41 | 2024-12-01 | 2025-12-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
BRP Kailas BESS | BRP Kailas BESS LLC | 201.29 | 2024-12-01 | 2025-12-01 | Taylor | WEST | SS Completed, FIS Started, No IA
BRP Elbus BESS | BRP Elbus BESS LLC | 201.11 | 2024-12-01 | 2025-12-01 | Caldwell | SOUTH | SS Completed, FIS Started, No IA
BRP Passu BESS | BRP Passu BESS LLC | 301.82 | 2024-12-01 | 2025-12-01 | Wilbarger | WEST | SS Completed, FIS Started, No IA
BRP Seine BESS | BRP Seine BESS LLC | 301.69 | 2024-12-01 | 2025-12-01 | Foard | WEST | SS Completed, FIS Started, No IA
BRP Sepik BESS | BRP Sepik BESS LLC | 200.85 | 2024-12-01 | 2025-12-01 | Mitchell | WEST | SS Completed, FIS Started, No IA
BRP Nile BESS | BRP Nile BESS LLC | 202.34 | 2024-12-01 | 2025-12-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
BRP Trivor BESS | BRP Trivor BESS LLC | 202.34 | 2024-12-01 | 2025-12-01 | Andrews | WEST | SS Completed, FIS Started, No IA
Zeya BESS | BRP Zeya BESS LLC | 255.33 | 2024-12-01 | 2025-12-01 | Galveston | HOUSTON | SS Completed, FIS Started, IA
BRP Brizo BESS | BRP Brizo BESS LLC | 143.85 | 2024-12-01 | 2025-12-01 | Victoria | SOUTH | SS Completed, FIS Started, No IA
BRP Charon BESS | BRP Charon BESS LLC | 410.81 | 2024-12-01 | 2025-12-01 | Fort Bend | HOUSTON | SS Completed, FIS Completed, No IA
BRP Volga BESS | BRP Volga BESS LLC | 174.63 | 2024-12-01 | 2025-12-01 | Dallas | NORTH | SS Completed, FIS Started, No IA
BRP Zelus BESS | BRP Zelus BESS LLC | 206.96 | 2024-12-01 | 2025-12-01 | Zapata | SOUTH | SS Completed, FIS Started, No IA
BRP Mekong BESS | BRP Mekong BESS LLC | 413.74 | 2024-12-01 | 2025-12-01 | Robertson | NORTH | SS Completed, FIS Completed, No IA
BRP De Los Santos BESS | BRP De Los Santos BESS LLC | 206.87 | 2024-12-01 | 2025-12-01 | Maverick | SOUTH | SS Completed, FIS Started, No IA
BRP Bachman BESS | BRP Bachman BESS LLC | 411.04 | 2024-12-01 | 2025-12-01 | Wharton | SOUTH | SS Completed, FIS Completed, No IA
XE Murat Storage | Liberty 1 Solar LLC | 60.14 | 2024-12-01 | 2025-12-01 | Harris | HOUSTON | SS Completed, FIS Completed, IA
Sunbelt Storage | Rose Hill Solar LLC | 52 | 2024-12-01 | 2025-12-01 | Kaufman | NORTH | SS Completed, FIS Started, No IA
Briggs Storage | Briggs Solar, LLC | 70.39 | 2024-12-01 | 2025-12-01 | Haskell | WEST | SS Completed, FIS Started, No IA
Longfellow BESS I | CENTURY GAS PROCESSING, LLC | 54.99 | 2024-12-01 | 2025-12-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Longfellow BESS II | CENTURY GAS PROCESSING, LLC | 105.75 | 2024-12-01 | 2025-12-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Stoneridge BESS | Stoneridge Solar, LLC | 101.9 | 2025-09-01 | 2025-12-01 | Milam | SOUTH | SS Completed, FIS Completed, IA
Alamosa Storage | Alamosa BESS West, LLC | 207.21 | 2025-01-01 | 2026-01-01 | Wilbarger | WEST | SS Completed, FIS Started, No IA
Fowler Ranch Storage | Crane BESS, LLC | 26.44 | 2025-01-01 | 2026-01-01 | Crane | WEST | SS Completed, FIS Started, No IA
BRP Pular BESS | BRP Pular BESS LLC | 233.1 | 2025-02-01 | 2026-02-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Bay Prairie Storage | San Bernard Storage, LLC | 201.02 | 2025-02-01 | 2026-02-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Morrow Lake Storage | Morrow Lake Storage, LLC | 201.13 | 2025-02-01 | 2026-02-01 | Frio | SOUTH | SS Completed, FIS Started, No IA
Mallard BESS | Mallard Energy Storage LLC | 256.18 | 2025-02-01 | 2026-02-01 | Collin | NORTH | SS Completed, FIS Started, No IA
Roadrunner Crossing BESS SLF | Roadrunner Crossing BESS | 40 | 2025-02-01 | 2026-02-01 | Eastland | NORTH | SS Completed, FIS Started, No IA
Glasgow Storage | Glasgow Solar LLC | 101 | 2025-11-01 | 2026-02-01 | Navarro | NORTH | SS Completed, FIS Completed, IA
Maleza Storage | Brush Storage, LLC | 150.83 | 2025-03-01 | 2026-03-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Amsterdam Storage | Cottonwood Bayou II Storage, LLC | 201.13 | 2025-03-01 | 2026-03-01 | Brazoria | COASTAL | SS Completed, FIS Started, IA
Austin Bayou Storage I | Austin Bayou Solar, LLC | 150.68 | 2025-03-01 | 2026-03-01 | Brazoria | COASTAL | SS Completed, FIS Completed, No IA
Austin Bayou Storage II | Austin Bayou Solar, LLC | 150.68 | 2025-03-01 | 2026-03-01 | Brazoria | COASTAL | SS Completed, FIS Completed, No IA
Austin Bayou Storage III | Austin Bayou Solar, LLC | 150.68 | 2025-03-01 | 2026-03-01 | Brazoria | COASTAL | SS Completed, FIS Completed, No IA
Maleza Storage II | Brush Storage, LLC | 256.1 | 2025-03-01 | 2026-03-01 | Wharton | SOUTH | SS Started, FIS Started, No IA
Arroyo Storage | BT Cantwell Solar, LLC | 183.76 | 2025-03-01 | 2026-03-01 | Cameron | COASTAL | SS Completed, FIS Completed, IA
Platinum Storage | Platinum Energy Storage LLC | 309.53 | 2025-03-01 | 2026-03-01 | Fannin | NORTH | SS Completed, FIS Started, IA
Blanquilla BESS | Blanquilla BESS LLC | 200.78 | 2025-03-01 | 2026-03-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Amber Storage | Belltown Power Texas | 50 | 2025-03-01 | 2026-03-01 | Cooke | NORTH | SS Completed, FIS Completed, No IA
Columbus Storage | EDP Renewables North America LLC | 51.3 | 2025-03-01 | 2026-03-01 | Colorado | SOUTH | SS Completed, FIS Started, No IA
Bexar ESS | Bexar ESS LLC | 102.6 | 2025-03-01 | 2026-03-01 | Bexar | SOUTH | SS Completed, FIS Not Started, IA
Soda Lake BESS 1 | Mendoza Trial BESS, LLC | 206.97 | 2025-03-01 | 2026-03-01 | Crane | WEST | SS Completed, FIS Started, No IA
Sherbino II BESS SLF | Phoenix Battery Storage, LLC | 18 | 2025-03-01 | 2026-03-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Crowned Heron BESS 2 | RWE Renewables | 150 | 2025-03-01 | 2026-03-01 | Fort Bend | HOUSTON | SS Completed, FIS Completed, No IA
Sowers Storage | Sowers Energy Storage LLC | 206.1 | 2025-12-01 | 2026-03-01 | Kaufman | NORTH | SS Completed, FIS Completed, IA
Bypass Battery Storage | Bypass BESS LLC | 206.9 | 2025-12-01 | 2026-03-01 | Fort Bend | HOUSTON | SS Completed, FIS Completed, IA
Topaz Energy Storage | WattBridge Energy, LLC | 202.32 | 2025-04-01 | 2026-04-01 | Galveston | HOUSTON | SS Completed, FIS Started, No IA
Outpost Storage | Hecate Energy Outpost Storage LLC | 508.1 | 2025-04-01 | 2026-04-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
Olympic BESS | SMT Olympic BESS LLC | 222.81 | 2025-04-01 | 2026-04-01 | Nueces | COASTAL | SS Completed, FIS Completed, No IA
Glory Bee Storage | Riley Solar LLC | 101 | 2025-04-01 | 2026-04-01 | Erath | NORTH | SS Completed, FIS Completed, No IA
Cross Trails Storage | Cross Trails Energy Storage Project, LLC | 58.29 | 2025-04-01 | 2026-04-01 | Scurry | WEST | SS Completed, FIS Started, No IA
Wizard BESS | Rocky Mountain Energy Holdings, LLC | 150.82 | 2025-04-01 | 2026-04-01 | Galveston | HOUSTON | SS Completed, FIS Started, IA
Destiny Storage | Destiny Storage, LLC | 201.11 | 2026-01-01 | 2026-04-01 | Harris | HOUSTON | SS Completed, FIS Completed, IA
Meridian BESS | Navitas Energy- Meredian BESS | 31.23 | 2025-05-01 | 2026-05-01 | Bosque | NORTH | SS Completed, FIS Started, No IA
Orchard Ray BESS | Pettus BESS | 51.85 | 2025-05-01 | 2026-05-01 | Bee | SOUTH | SS Completed, FIS Started, No IA
Hinkell BESS | Reveille BESS | 78.05 | 2025-05-01 | 2026-05-01 | La Salle | SOUTH | SS Completed, FIS Started, No IA
Beeman BESS | Waelder BESS | 50.18 | 2025-05-01 | 2026-05-01 | Gonzales | SOUTH | SS Completed, FIS Started, No IA
Bordertown BESS | Bordertown BESS LLC | 106.15 | 2025-05-01 | 2026-05-01 | Starr | SOUTH | SS Completed, FIS Started, IA
Fagus Storage SLF | Greenalia Energy Storage MISAE II LLC | 0 | 2025-05-01 | 2026-05-01 | Childress | PANHANDLE | SS Completed, FIS Started, No IA
Evergreen Storage | Evergreen Energy LLC | 100 | 2025-05-01 | 2026-05-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Hovey Energy Storage | Barilla Solar, LLC | 23 | 2025-05-01 | 2026-05-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Indigo Storage | Indigo Storage | 50.08 | 2025-05-01 | 2026-05-01 | Fisher | WEST | SS Completed, FIS Started, No IA
MICOT BESS | UR-Silo DevCo LLC | 150 | 2025-05-01 | 2026-05-01 | Montgomery | HOUSTON | SS Completed, FIS Started, No IA
Arana Creek Batt | Arana Creek LLC | 153.5 | 2025-05-01 | 2026-05-01 | Kleberg | COASTAL | SS Completed, FIS Started, No IA
Kingfisher Energy Storage | Nopalosa Energy Storage, LLC | 204.97 | 2025-05-01 | 2026-05-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
Cascade Storage | Oyster Creek LLC | 250 | 2025-05-01 | 2026-05-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Hana Springs BESS | Black Mountain Energy Storage II LLC | 100.8 | 2025-05-01 | 2026-05-01 | Lampasas | NORTH | SS Completed, FIS Started, No IA
Mesa View Storage | Mesa View Storage, LLC | 501.9 | 2025-05-01 | 2026-05-01 | Upton | WEST | SS Completed, FIS Started, No IA
Brotherton Storage | Belltown Power Texas 2 | 176.13 | 2025-05-01 | 2026-05-01 | Anderson | NORTH | SS Completed, FIS Completed, No IA
BRP Denali BESS | BRP Denali BESS LLC | 258.41 | 2025-06-01 | 2026-06-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
Vaca Storage | Long Mount Storage, LLC | 101 | 2025-06-01 | 2026-06-01 | Calhoun | COASTAL | SS Completed, FIS Started, No IA
Paradiso BESS | VESI 13 | 100.92 | 2025-06-01 | 2026-06-01 | Atascosa | SOUTH | SS Completed, FIS Started, No IA
Las Moras Battery | Las Moras Storage, LLC | 101 | 2025-06-01 | 2026-06-01 | Kinney | SOUTH | SS Completed, FIS Started, No IA
BRP Chena BESS | BRP Chena BESS LLC | 202.32 | 2025-06-01 | 2026-06-01 | Tarrant | NORTH | SS Completed, FIS Started, No IA
Fort Duncan BESS | Fort Duncan BESS LLC | 106.15 | 2025-06-01 | 2026-06-01 | Maverick | SOUTH | SS Completed, FIS Started, IA
Castor BESS | BRP Castor BESS LLC | 205.39 | 2025-06-01 | 2026-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, IA
Camellia Storage | Camellia Storage Project LLC | 90.76 | 2025-06-01 | 2026-06-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Desna BESS | BRP Desna BESS LLC | 205.46 | 2025-06-01 | 2026-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, IA
BRP Artemis BESS | BRP Artemis BESS LLC | 411.32 | 2025-06-01 | 2026-06-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
BRP Hestia BESS | BRP Hestia BESS LLC | 29.05 | 2025-06-01 | 2026-06-01 | Edwards | SOUTH | SS Completed, FIS Started, No IA
Tejano Storage | Tejano Storage, LLC | 152 | 2025-06-01 | 2026-06-01 | Victoria | SOUTH | SS Completed, FIS Started, No IA
Red Egret BESS | Red Egret LLC | 310.58 | 2025-06-01 | 2026-06-01 | Galveston | HOUSTON | SS Completed, FIS Started, IA
Albatross BESS | Albatross Solar, LLC | 50.4 | 2025-06-01 | 2026-06-01 | McLennan | NORTH | SS Completed, FIS Started, No IA
Saltillo Storage | SALTILLO STORAGE | 101 | 2025-06-01 | 2026-06-01 | Bastrop | SOUTH | SS Completed, FIS Started, No IA
Pinewood BESS | Brazoria Solar II, LLC | 100.9 | 2025-06-01 | 2026-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Big Five Storage | TX BESS 3 LLC | 102.18 | 2025-06-01 | 2026-06-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Halcon Storage | TX BESS A LLC | 132.65 | 2025-06-01 | 2026-06-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
East Blackland Battery Storage SLF | DERIVA ENERGY STORAGE, LLC | 75 | 2025-06-01 | 2026-06-01 | Travis | SOUTH | SS Completed, FIS Started, No IA
NavBoot BESS | Navboot BESS LLC | 303.7 | 2025-06-01 | 2026-06-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Driet BESS | Weimar BESS | 150.52 | 2025-06-01 | 2026-06-01 | Colorado | SOUTH | SS Completed, FIS Started, No IA
Pledgor BESS | Pledgor BESS | 100.33 | 2025-06-01 | 2026-06-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Waterloo BESS 1 | Waterloo Solar, LLC | 105.64 | 2025-06-01 | 2026-06-01 | Bastrop | SOUTH | SS Completed, FIS Started, No IA
Dan Kearney BESS | Dan Kearney BESS LLC | 200.78 | 2025-06-01 | 2026-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Albatross BESS 2 | Albatross Solar, LLC | 107.5 | 2025-06-01 | 2026-06-01 | McLennan | NORTH | SS Started, FIS Started, No IA
Evelyn Battery Energy Storage System | Evelyn Energy Storage LLC | 221.3 | 2025-06-01 | 2026-06-01 | Galveston | HOUSTON | SS Completed, FIS Started, IA
Pequin Energy Storage | Pequin Energy Storage, LLC | 103.4 | 2025-06-01 | 2026-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Cartwheel BESS 2 | RWE Renewables | 156.91 | 2025-06-01 | 2026-06-01 | Hopkins | NORTH | SS Completed, FIS Completed, No IA
Backwater Storage | Backwater Solar LLC | 100 | 2025-06-01 | 2026-06-01 | Cooke | NORTH | SS Completed, FIS Completed, No IA
Masroor Storage | Masroor Energy Storage LLC | 203 | 2025-06-01 | 2026-06-01 | Fannin | NORTH | SS Completed, FIS Completed, No IA
Pine Forest BESS | Pine Forest Hybrid I, LLC | 421 | 2025-06-01 | 2026-06-01 | Hopkins | NORTH | SS Completed, FIS Completed, IA
Petunia Storage Project | Petunia Storage Project LLC | 231.86 | 2025-06-01 | 2026-06-01 | Milam | SOUTH | SS Completed, FIS Started, No IA
Cold Creek Storage | Cold Creek Solar LLC | 172.4 | 2025-06-01 | 2026-06-01 | Schleicher | WEST | SS Completed, FIS Started, No IA
SOSA Storage | SOSA Energy Center LLC | 157.36 | 2026-03-01 | 2026-06-01 | Madison | NORTH | SS Completed, FIS Completed, IA
Lunis Creek Storage SLF | Lunis Creek Solar Project, LLC | 0 | 2025-07-01 | 2026-07-01 | Jackson | SOUTH | SS Completed, FIS Started, No IA
Blevins Storage | Blevins Solar, LLC | 181.3 | 2025-07-01 | 2026-07-01 | Falls | NORTH | SS Completed, FIS Started, IA
Mitchell Plant Road Storage | DHI POWER, LLC | 201.6 | 2025-07-01 | 2026-07-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Shamrock Energy Storage (SLF) | Shamrock Interconnection LLC | 0 | 2025-07-01 | 2026-07-01 | Crockett | WEST | SS Completed, FIS Completed, No IA
Legato BESS | Legato Storage, LLC | 202.65 | 2025-07-01 | 2026-07-01 | Wise | NORTH | SS Completed, FIS Started, No IA
Sonata BESS | Sonata Storage, LLC | 83.86 | 2025-07-01 | 2026-07-01 | Colorado | SOUTH | SS Completed, FIS Started, No IA
Fortissimo BESS | Fortissimo BESS, LCC | 202.65 | 2025-07-01 | 2026-07-01 | Montague | NORTH | SS Completed, FIS Started, No IA
Palmvalley Storage | Palmvalley Energy Storage LLC | 100 | 2025-07-01 | 2026-07-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Ochoa Energy Storage | Ochoa Energy Storage LLC | 260.8 | 2025-07-01 | 2026-07-01 | Waller | HOUSTON | SS Completed, FIS Started, No IA
Whiskey BESS | UR-Silo DevCo LLC | 153.72 | 2025-07-01 | 2026-07-01 | Van Zandt | NORTH | SS Completed, FIS Started, No IA
Zorro BESS | UR-Silo DevCo LLC | 153.69 | 2025-07-01 | 2026-07-01 | Van Zandt | NORTH | SS Completed, FIS Started, No IA
Dori BQ BESS | Sunnyside Energy LLC | 154 | 2025-07-01 | 2026-07-01 | Harris | HOUSTON | SS Completed, FIS Completed, IA
MRG Goody Storage | MRG Goody Solar Project LLC | 50.4 | 2025-07-01 | 2026-07-01 | Lamar | NORTH | SS Completed, FIS Completed, No IA
Shepard Energy Storage | Shepard Energy Storage LLC | 263.2 | 2025-07-01 | 2026-07-01 | Galveston | HOUSTON | SS Completed, FIS Started, IA
Tidwell Prairie Storage 1 | Tidwell Prairie LLC | 200 | 2025-07-01 | 2026-07-01 | Robertson | NORTH | SS Completed, FIS Started, IA
TE Smith Storage | BT Smith Storage, LLC | 125.36 | 2025-07-01 | 2026-07-01 | Rockwall | NORTH | SS Completed, FIS Started, IA
Citrus Flatts BESS | Citrus Flatts Energy Center, LLC | 100.8 | 2025-07-01 | 2026-07-01 | Cameron | COASTAL | SS Completed, FIS Started, IA
Aldrin 138 BESS | Aldrin Energy Storage LLC | 207 | 2025-07-01 | 2026-07-01 | Brazoria | COASTAL | SS Completed, FIS Started, IA
Aldrin 345 BESS | Aldrin Energy Storage LLC | 362 | 2025-07-01 | 2026-07-01 | Brazoria | COASTAL | SS Completed, FIS Completed, No IA
Black & Gold Energy Storage | RES America Developments Inc. | 254.58 | 2025-07-01 | 2026-07-01 | Menard | WEST | SS Completed, FIS Started, No IA
Gaia Storage | Gaia Solar, LLC | 76.83 | 2025-07-01 | 2026-07-01 | Navarro | NORTH | SS Completed, FIS Started, IA
Berkman Storage | Berkman Storage, LLC | 150.86 | 2026-04-01 | 2026-07-01 | Galveston | HOUSTON | SS Completed, FIS Completed, IA
Ringtail Ridge Storage | KCE TX 26, LLC | 100.57 | 2025-08-01 | 2026-08-01 | Kendall | SOUTH | SS Completed, FIS Started, No IA
Harley Hand Storage | Hecate Energy Harley Hand Solar LLC | 509 | 2025-08-01 | 2026-08-01 | Nolan | WEST | SS Completed, FIS Started, No IA
Lan Battery SLF | General Solar, LLC | 0 | 2025-08-01 | 2026-08-01 | Lamar | NORTH | SS Completed, FIS Started, No IA
Pintail Pass BESS | Pintail Pass BESS, LLC | 207.18 | 2025-08-01 | 2026-08-01 | San Patricio | COASTAL | SS Completed, FIS Started, IA
Midpoint Storage | Midpoint Solar, LLC | 52.24 | 2025-08-01 | 2026-08-01 | Hill | NORTH | SS Completed, FIS Started, IA
Lucas Storage SLF | Clip Road Solar, LLC | 0 | 2025-08-01 | 2026-08-01 | Goliad | SOUTH | SS Completed, FIS Started, No IA
Noria Storage | Noria Hondo Solar, LLC | 75 | 2025-09-01 | 2026-09-01 | Nueces | COASTAL | SS Completed, FIS Started, IA
Trelas | Trelasol, LLC | 200.83 | 2025-09-01 | 2026-09-01 | McCulloch | SOUTH | SS Completed, FIS Started, No IA
Marcus Energy Storage | Marcus Energy Storage, LLC | 201.04 | 2025-09-01 | 2026-09-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Iron Belt Energy Storage | Iron Belt Energy Storage Project, LLC | 401.9 | 2025-09-01 | 2026-09-01 | Borden | WEST | SS Completed, FIS Started, IA
Fike BESS | BRP Blue Topaz 9, LLC | 200.83 | 2025-09-01 | 2026-09-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Diaz BESS | BRP Blue Topaz 10, LLC | 244 | 2025-09-01 | 2026-09-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
John Bull BESS | BRP BLUE TOPAZ 13, LLC | 147.42 | 2025-09-01 | 2026-09-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Harden BESS | BRP Blue Topaz 14, LLC | 301.29 | 2025-09-01 | 2026-09-01 | Waller | HOUSTON | SS Completed, FIS Started, No IA
Eighteenmile Storage SLF | Weser Solar, LLC | 0 | 2025-09-01 | 2026-09-01 | Goliad | SOUTH | SS Completed, FIS Started, No IA
Bayside BESS | Bayside BESS | 507.8 | 2025-09-01 | 2026-09-01 | Victoria | SOUTH | SS Completed, FIS Started, No IA
Hawkins BESS | BRP BLUE TOPAZ 7, LLC | 150.45 | 2025-09-01 | 2026-09-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Palacios BESS | BRP BLUE TOPAZ 11, LLC | 125.69 | 2025-09-01 | 2026-09-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Marengo BESS | BRP BLUE TOPAZ 8, LLC | 120.72 | 2025-09-01 | 2026-09-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Lyford Energy | Lyford Energy, LLC | 101.2 | 2025-09-01 | 2026-09-01 | Willacy | COASTAL | SS Completed, FIS Started, No IA
Canyonland Energy Storage | Canyonland Energy Storage, LLC | 101.2 | 2025-09-01 | 2026-09-01 | Comanche | NORTH | SS Completed, FIS Started, No IA
Yaupon Storage SLF | Yaupon Solar, LLC | 0 | 2025-09-01 | 2026-09-01 | Milam | SOUTH | SS Completed, FIS Started, IA
HOPSLAM BESS | Momentum LRC Holdco LLC | 151.11 | 2025-09-01 | 2026-09-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Brushy Creek Storage SLF | Brushy Creek Solar | 0 | 2025-09-01 | 2026-09-01 | Tom Green | WEST | SS Completed, FIS Started, No IA
Schoolhouse BESS | Schoolhouse Storage, LLC | 150.68 | 2025-09-01 | 2026-09-01 | Lee | SOUTH | SS Completed, FIS Started, No IA
Houston BESS | SMT Houston | 227.9 | 2025-09-01 | 2026-09-01 | Harris | HOUSTON | SS Completed, FIS Completed, No IA
Seven Flags BESS | Seven Flags BESS LLC | 102.62 | 2025-09-01 | 2026-09-01 | Webb | SOUTH | SS Completed, FIS Started, IA
Tierra Seca BESS | Tierra Seca BESS LLC | 101.21 | 2025-09-01 | 2026-09-01 | Val Verde | WEST | SS Completed, FIS Started, IA
Eldora BESS | Eldora Energy LLC | 201.31 | 2026-06-01 | 2026-09-01 | Matagorda | COASTAL | SS Completed, FIS Completed, IA
Rocinante BESS | Brush Country Solar Project, LLC | 33 | 2025-10-01 | 2026-10-01 | Gonzales | SOUTH | SS Completed, FIS Started, IA
Bronze Quinta Storage | KCE TX 28, LLC | 103.51 | 2025-10-01 | 2026-10-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Raven Storage | Raven Storage, LLC | 101.83 | 2025-10-01 | 2026-10-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Mercedes II BESS | SMT Mercedes II, LLC | 227.87 | 2025-10-01 | 2026-10-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Pinnington Storage | Hecate Energy Longhorn Storage LLC | 508.7 | 2025-10-01 | 2026-10-01 | Jack | NORTH | SS Completed, FIS Completed, No IA
Hanson Storage | Hanson Solar, LLC | 101.39 | 2025-10-01 | 2026-10-01 | Coleman | WEST | SS Completed, FIS Started, IA
DOS RIOS ENERGY STORAGE SLF | DOS RIOS SOLAR, LLC | 0 | 2025-10-01 | 2026-10-01 | Milam | SOUTH | SS Completed, FIS Started, No IA
Liberty Senate Energy Storage 1 | Senate Solar LLC | 207.4 | 2025-10-01 | 2026-10-01 | Jack | NORTH | SS Completed, FIS Completed, No IA
Cado Storage | Cado Storage, LLC | 205.2 | 2025-10-01 | 2026-10-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
High Plains Storage | ROBP Holdings, LLC | 157.7 | 2025-10-01 | 2026-10-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Deer BESS | GRS BESS Texas Two | 102.31 | 2025-10-01 | 2026-10-01 | Lamar | NORTH | SS Completed, FIS Started, No IA
BRP Pictor BESS | BRP Pictor BESS LLC | 201.07 | 2025-11-01 | 2026-11-01 | Crane | WEST | SS Completed, FIS Started, No IA
Rose Quartz BESS | Rose Quartz BESS, LLC | 101.41 | 2025-11-01 | 2026-11-01 | Dimmit | SOUTH | SS Completed, FIS Started, No IA
Big Elm Storage | Big Elm Storage, LLC | 102.8 | 2025-11-01 | 2026-11-01 | Bell | NORTH | SS Completed, FIS Started, No IA
Kennedy Storage | Kennedy Bypass Solar LLC | 25.3 | 2025-11-01 | 2026-11-01 | Navarro | NORTH | SS Completed, FIS Started, No IA
Blue Sky Storage SLF | UKA North America, LLC | 0 | 2025-11-01 | 2026-11-01 | Crockett | WEST | SS Completed, FIS Started, No IA
Rubicon Power BESS | Rubicon Power LLC | 301.38 | 2025-11-01 | 2026-11-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Royal River BESS | Royal River LLC | 309 | 2025-11-01 | 2026-11-01 | Brazoria | COASTAL | SS Completed, FIS Completed, No IA
GALVANIC BESS | CED Development Inc | 100 | 2025-11-01 | 2026-11-01 | Kinney | SOUTH | SS Completed, FIS Started, No IA
SUNSETTER BESS | CED Development Inc. | 100 | 2025-11-01 | 2026-11-01 | Uvalde | SOUTH | SS Completed, FIS Started, No IA
Solara BESS 1 | CED Development Inc. | 150 | 2025-11-01 | 2026-11-01 | Jones | WEST | SS Completed, FIS Started, No IA
Solara BESS 2 | CED Development Inc. | 150 | 2025-11-01 | 2026-11-01 | Jones | WEST | SS Completed, FIS Started, No IA
Long Point Storage | Long Point Storage, LLC | 100.62 | 2025-12-01 | 2026-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, IA
BRP Crater BESS | BRP Crater BESS LLC | 310.31 | 2025-12-01 | 2026-12-01 | Howard | WEST | SS Completed, FIS Started, No IA
BRP Quela BESS | BRP Quela BESS LLC | 303.74 | 2025-12-01 | 2026-12-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
BRP Kabru BESS | BRP Kabru BESS LLC | 202.45 | 2025-12-01 | 2026-12-01 | Andrews | WEST | SS Completed, FIS Started, No IA
BRP Rhine BESS | BRP Rhine BESS LLC | 206.89 | 2025-12-01 | 2026-12-01 | Ward | WEST | SS Completed, FIS Completed, No IA
BRP Pyxis BESS | BRP Pyxis BESS LLC | 206.87 | 2025-12-01 | 2026-12-01 | Ward | WEST | SS Completed, FIS Completed, No IA
BRP Kamet BESS | BRP Kamet BESS LLC | 202.46 | 2025-12-01 | 2026-12-01 | Andrews | WEST | SS Completed, FIS Started, No IA
BRP Batura BESS | BRP Batura BESS LLC | 251.65 | 2025-12-01 | 2026-12-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
BRP Diran BESS | BRP Diran BESS LLC | 100.63 | 2025-12-01 | 2026-12-01 | Wharton | SOUTH | SS Completed, FIS Completed, No IA
Big River BESS | Rio Grande River Solar LLC | 51.26 | 2025-12-01 | 2026-12-01 | Zapata | SOUTH | SS Completed, FIS Started, No IA
BRP Aras BESS | BRP Aras BESS LLC | 303.59 | 2025-12-01 | 2026-12-01 | Upton | WEST | SS Completed, FIS Started, No IA
BRP Parana BESS | BRP Parana BESS | 303.67 | 2025-12-01 | 2026-12-01 | Guadalupe | SOUTH | SS Completed, FIS Started, No IA
Avila BESS | BRP Avila BESS LLC | 164.28 | 2025-12-01 | 2026-12-01 | Pecos | WEST | SS Completed, FIS Started, IA
BRP Yarra BESS | BRP Yarra BESS LLC | 205.36 | 2025-12-01 | 2026-12-01 | Dallas | NORTH | SS Completed, FIS Started, No IA
BRP Crios BESS | BRP Crios BESS LLC | 87.37 | 2025-12-01 | 2026-12-01 | Comanche | NORTH | SS Completed, FIS Started, No IA
White Wing I Energy Storage | White Wing I Energy Storage LLC | 101.63 | 2025-12-01 | 2026-12-01 | San Patricio | COASTAL | SS Completed, FIS Started, No IA
White Wing II Energy Storage | White Wing II Energy Storage LLC | 101.63 | 2025-12-01 | 2026-12-01 | San Patricio | COASTAL | SS Completed, FIS Started, No IA
Honeycomb Storage SLF | Honeycomb Solar, LLC | 0 | 2025-12-01 | 2026-12-01 | Bee | SOUTH | SS Completed, FIS Started, IA
Gunnar BESS | BRP Blue Topaz 6, LLC | 203 | 2025-12-01 | 2026-12-01 | Hidalgo | SOUTH | SS Completed, FIS Started, IA
Box Canyon Energy Storage | Box Canyon Energy Storage Project, LLC | 306.34 | 2025-12-01 | 2026-12-01 | Callahan | WEST | SS Completed, FIS Started, No IA
Bobcat Cameron BESS | Bobcat BESS, LLC | 200.78 | 2025-12-01 | 2026-12-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
South Loop Energy Center | Concurrent Holdco LLC | 161.3 | 2025-12-01 | 2026-12-01 | Bexar | SOUTH | SS Started, FIS Started, No IA
Pearl Crescent Storage | RWE Solar Development, LLC | 50.26 | 2025-12-01 | 2026-12-01 | Colorado | SOUTH | SS Completed, FIS Started, No IA
Callisto II Energy Center | Callisto II Energy Center LLC | 406.06 | 2025-12-01 | 2026-12-01 | Harris | HOUSTON | SS Completed, FIS Started, IA
Bird Dog BESS | VESI 37 LLC | 60 | 2025-12-01 | 2026-12-01 | Live Oak | SOUTH | SS Completed, FIS Started, IA
Little Ridge Storage | TX BESS B LLC | 252 | 2025-12-01 | 2026-12-01 | Collin | NORTH | SS Completed, FIS Started, No IA
Pato Blanco Storage | TX BESS 4, LLC | 71.34 | 2025-12-01 | 2026-12-01 | Fort Bend | HOUSTON | SS Completed, FIS Started, No IA
Exodus BESS | Exodus Solar LLC | 201.36 | 2025-12-01 | 2026-12-01 | Caldwell | SOUTH | SS Completed, FIS Started, No IA
Carolina Storage Friendswood | CSE Storage, LLC | 105.08 | 2025-12-01 | 2026-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Painted Horse Storage | RWE Solar Development, LLC | 53.22 | 2025-12-01 | 2026-12-01 | Wilson | SOUTH | SS Completed, FIS Started, No IA
Razorbill Storage | RWE Solar Development, LLC | 120 | 2025-12-01 | 2026-12-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Third Coast BESS | Third Coast BESS LLC | 102.84 | 2025-12-01 | 2026-12-01 | Jackson | SOUTH | SS Completed, FIS Started, IA
San Perlita BESS 1 | RWE Renewables | 150 | 2025-12-01 | 2026-12-01 | Willacy | COASTAL | SS Completed, FIS Started, No IA
San Perlita BESS 2 | RWE Renewables | 150 | 2025-12-01 | 2026-12-01 | Willacy | COASTAL | SS Completed, FIS Started, No IA
McCamey's Castle Battery | Castle Storage, LLC | 409.6 | 2025-12-01 | 2026-12-01 | Upton | WEST | SS Completed, FIS Started, No IA
Wooderson Energy Storage | Wooderson Energy Storage, LLC | 306.4 | 2025-12-01 | 2026-12-01 | Jack | NORTH | SS Started, FIS Started, No IA
Nymphaea Storage | Nymphaea Solar, LLC | 61 | 2025-12-01 | 2026-12-01 | Wichita | WEST | SS Completed, FIS Completed, No IA
Midnight Sun Energy Storage | RES America Developments Inc. | 510 | 2025-12-01 | 2026-12-01 | Crockett | WEST | SS Completed, FIS Started, No IA
Starr Storage | Falcon Lake Storage, LLC | 0 | 2025-12-01 | 2026-12-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
Ramsey Storage | Hecate Energy Ramsey Storage LLC | 510.4 | 2025-12-01 | 2026-12-01 | Wharton | SOUTH | SS Completed, FIS Started, IA
Eval Storage | Hecate Grid East Valley Storage LLC | 255 | 2025-12-01 | 2026-12-01 | Cameron | COASTAL | SS Completed, FIS Started, IA
Bowstring BESS | Longbow Energy Storage, LLC | 155 | 2025-12-01 | 2026-12-01 | San Patricio | COASTAL | SS Completed, FIS Completed, No IA
Anson BAT | Anson Solar Center, LLC | 156.86 | 2025-12-01 | 2026-12-01 | Jones | WEST | SS Completed, FIS Started, No IA
Eagle Springs Storage | Eagle Springs Solar, LLC | 55.1 | 2025-12-01 | 2026-12-01 | Delta | NORTH | SS Completed, FIS Started, No IA
BRP Merope BESS | BRP Merope BESS LLC | 413.74 | 2025-12-01 | 2026-12-01 | Comanche | NORTH | SS Completed, FIS Started, No IA
Amador Storage | BT Amador Storage, LLC | 100.92 | 2025-12-01 | 2026-12-01 | Van Zandt | NORTH | SS Completed, FIS Completed, IA
Rutile BESS | Rutile BESS, LLC | 100.65 | 2025-12-01 | 2026-12-01 | Runnels | WEST | SS Completed, FIS Started, No IA
Rogers Draw BESS | ROGERS DRAW ENERGY STORAGE, LLC | 148.61 | 2025-12-01 | 2026-12-01 | Gillespie | SOUTH | SS Completed, FIS Not Started, IA
Shaula I BESS | Shaula Energy Project LLC | 86.88 | 2025-12-01 | 2026-12-01 | DeWitt | SOUTH | SS Completed, FIS Started, No IA
Staccato BESS | Staccato Storage, LLC | 202.65 | 2025-12-01 | 2026-12-01 | Fayette | SOUTH | SS Completed, FIS Started, No IA
Hector Storage | Hector Solar, LLC | 42.69 | 2025-12-01 | 2026-12-01 | Navarro | NORTH | SS Completed, FIS Completed, No IA
Elan BESS | Elan BESS, LLC | 202.65 | 2025-12-01 | 2026-12-01 | Fort Bend | HOUSTON | SS Completed, FIS Started, No IA
Second Division Storage | Mound Creek Storage, LLC | 0 | 2025-12-01 | 2026-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Dios BESS | Dios BESS, LLC | 201.08 | 2025-12-01 | 2026-12-01 | Jackson | SOUTH | SS Completed, FIS Started, No IA
Peridot Storage | BT Castro Storage, LLC | 50.48 | 2025-12-01 | 2026-12-01 | Zavala | SOUTH | SS Completed, FIS Started, No IA
Tres Rios Ranch BESS | LectricWind LLC | 0 | 2025-12-01 | 2026-12-01 | Upton | WEST | SS Completed, FIS Started, No IA
Unruh Storage | BT Unruh Solar, LLC | 50.47 | 2025-12-01 | 2026-12-01 | Red River | NORTH | SS Completed, FIS Started, No IA
Crowded Star I BESS | Jones City Solar, LLC | 101.37 | 2025-12-01 | 2026-12-01 | Jones | WEST | SS Completed, FIS Started, No IA
Crowded Star II BESS | Jones City Solar II, LLC | 101.37 | 2025-12-01 | 2026-12-01 | Jones | WEST | SS Completed, FIS Started, No IA
Bell Creek BESS | West Columbia BESS1 LLC | 200.9 | 2025-12-01 | 2026-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Diver Energy Storage SLF | NextEra Energy Interconnection Holdings, LLC | 0 | 2025-12-01 | 2026-12-01 | Limestone | NORTH | SS Completed, FIS Started, No IA
Rayos del Sol BESS | Rayos Del Sol Solar Project | 100.26 | 2025-12-01 | 2026-12-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
First Capitol BESS | First Capitol BESS, LLC | 256.2 | 2025-12-01 | 2026-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Independence Trail Storage | KCE TX 16, LLC | 100 | 2026-01-01 | 2027-01-01 | Childress | PANHANDLE | SS Completed, FIS Started, No IA
Hive Hollows Storage | KCE TX 27, LLC | 103.51 | 2026-01-01 | 2027-01-01 | Bell | NORTH | SS Completed, FIS Started, No IA
Citrus Grove Energy Storage | SANTA ANA ENERGY STORAGE I LLC | 204.93 | 2026-01-01 | 2027-01-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Padua Grid BESS Unit 2 | Padua Grid, LLC | 150.87 | 2026-01-01 | 2027-01-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
Sengun BESS | BRP Blue Topaz 12, LLC | 200.89 | 2026-01-01 | 2027-01-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Houston IV BESS | SMT Houston IV LLC | 168.6 | 2026-01-01 | 2027-01-01 | Harris | HOUSTON | SS Completed, FIS Completed, No IA
Bowhead Storage | Baffin Bay Solar, LLC | 40 | 2026-01-01 | 2027-01-01 | Kleberg | COASTAL | SS Completed, FIS Started, No IA
APV Plumwood Storage | APV Lonestar Energy LLC | 200.82 | 2026-01-01 | 2027-01-01 | Chambers | HOUSTON | SS Completed, FIS Completed, No IA
Hooper Storage | BT Brown Solar, LLC | 30.68 | 2026-01-01 | 2027-01-01 | Lee | SOUTH | SS Completed, FIS Completed, No IA
Bowhead Storage 2 | Baffin Bay Solar, LLC | 0 | 2026-01-01 | 2027-01-01 | Kleberg | COASTAL | SS Completed, FIS Started, No IA
Venus Mill Storage | KCE TX 14, LLC | 100.8 | 2026-01-01 | 2027-01-01 | Ellis | NORTH | SS Completed, FIS Started, No IA
BRP Tucana BESS | BRP Tucana BESS LLC | 206.98 | 2026-01-01 | 2027-01-01 | Andrews | WEST | SS Completed, FIS Started, No IA
Stinger Energy Storage | Stinger Energy Storage LLC | 200.8 | 2026-01-01 | 2027-01-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Quail Run Storage System | to be determined | 50 | 2026-02-01 | 2027-02-01 | Ector | WEST | SS Completed, FIS Started, No IA
Radian Storage SLF | IP Radian BESS, LLC | 0 | 2026-02-01 | 2027-02-01 | Brown | NORTH | SS Completed, FIS Started, No IA
Goldeneye BESS | Black Mountain Energy Storage II | 201.6 | 2026-02-01 | 2027-02-01 | Bell | NORTH | SS Completed, FIS Completed, IA
VERTUS ENERGY STORAGE | VERTUS ENERGY STORAGE LLC | 401.4 | 2026-02-01 | 2027-02-01 | Galveston | HOUSTON | SS Completed, FIS Started, No IA
SOUTHERN SELECT ENERGY STORAGE | SOUTHERN SELECT ENERGY STORAGE LLC | 404.3 | 2026-02-01 | 2027-02-01 | Galveston | HOUSTON | SS Completed, FIS Started, No IA
Harper Energy Storage | VESI 31 LLC | 82.42 | 2026-02-01 | 2027-02-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Purple Sage BESS 1 | Purple Sage, LLC | 156 | 2026-02-01 | 2027-02-01 | Collin | NORTH | SS Completed, FIS Completed, No IA
Purple Sage BESS 2 | Purple Sage, LLC | 156 | 2026-02-01 | 2027-02-01 | Collin | NORTH | SS Completed, FIS Completed, No IA
Bufflehead BESS | Black Mountain Energy Storage II | 100.8 | 2026-02-01 | 2027-02-01 | Collin | NORTH | SS Completed, FIS Completed, IA
Picadillo BESS | Black Mountain Energy Storage II | 100.83 | 2026-02-01 | 2027-02-01 | Martin | WEST | SS Completed, FIS Completed, IA
Huisache BESS | Novis Renewables, LLC | 100.67 | 2026-02-01 | 2027-02-01 | Wilson | SOUTH | SS Completed, FIS Started, No IA
Fort Concho Energy storage | Rocky Mountain Energy Development, LLC | 251.15 | 2026-02-01 | 2027-02-01 | Tom Green | WEST | SS Completed, FIS Started, No IA
Zeppelin Energy Storage | ZEPPELIN ENERGY STORAGE LLC | 163.93 | 2026-02-01 | 2027-02-01 | Tom Green | WEST | SS Completed, FIS Started, No IA
AP Greenport | AP Greenport | 100.45 | 2026-02-01 | 2027-02-01 | Travis | SOUTH | SS Completed, FIS Completed, No IA
Middlebrook BESS | Middlebrook Solar LLC | 302.94 | 2026-02-01 | 2027-02-01 | Nacogdoches | NORTH | SS Completed, FIS Started, No IA
Dragan Storage | Hecate Grid Dragan Storage LLC | 408.3 | 2026-02-01 | 2027-02-01 | Comanche | NORTH | SS Completed, FIS Started, No IA
Adelite Storage | Adelite Storage Project LLC | 231.88 | 2026-02-01 | 2027-02-01 | Milam | SOUTH | SS Completed, FIS Started, No IA
Steppe Reserve Storage | KCE TX 25, LLC | 51.9 | 2026-03-01 | 2027-03-01 | Dimmit | SOUTH | SS Completed, FIS Started, No IA
Proving Ground BESS | Lantana Solar LLC | 42.9 | 2026-03-01 | 2027-03-01 | Schleicher | WEST | SS Completed, FIS Started, No IA
Rowdy Creek BESS SLF | Rowdy Creek Solar LLC | 0 | 2026-03-01 | 2027-03-01 | Lamar | NORTH | SS Completed, FIS Started, No IA
Tehuacana Creek BESS SLF | Tehuacana Creek Solar LLC | 0 | 2026-03-01 | 2027-03-01 | Navarro | NORTH | SS Completed, FIS Completed, No IA
Smokey Willie BESS SLF | Neches Solar, LLC | 0 | 2026-03-01 | 2027-03-01 | Anderson | NORTH | SS Completed, FIS Completed, No IA
Project Lynx BESS | Corpus Battery Storage, LLC | 262.09 | 2026-03-01 | 2027-03-01 | Nueces | COASTAL | SS Completed, FIS Started, IA
Sisters Storage | 174 Power Global Properties | 208.89 | 2026-03-01 | 2027-03-01 | Ector | WEST | SS Completed, FIS Started, No IA
Cairos Storage | Cairos Solar, LLC | 77.28 | 2026-03-01 | 2027-03-01 | Kinney | SOUTH | SS Completed, FIS Started, No IA
Moonlight Sonata BESS | Samsung Solar Energy 2, LLC | 201.08 | 2026-03-01 | 2027-03-01 | Colorado | SOUTH | SS Completed, FIS Started, No IA
Trinidad ESS Addition | LUMINANT GENERATION COMPANY LLC | 110 | 2026-03-01 | 2027-03-01 | Henderson | NORTH | SS Completed, FIS Completed, No IA
Padrino BESS | Hill Solar II, LLC | 100.77 | 2026-03-01 | 2027-03-01 | Hill | NORTH | SS Completed, FIS Started, No IA
Tidwell Prairie II Batt | TIDWELL PRAIRIE LLC | 200 | 2026-03-01 | 2027-03-01 | Robertson | NORTH | SS Completed, FIS Started, No IA
Sloan Storage | Sloan Energy Storage LLC | 200.9 | 2026-03-01 | 2027-03-01 | Henderson | NORTH | SS Completed, FIS Started, No IA
Demeter Storage | Demeter Solar, LLC | 65 | 2026-03-01 | 2027-03-01 | Caldwell | SOUTH | SS Completed, FIS Started, No IA
Wang Storage SLF | BT Yixin Solar, LLC | 0 | 2026-03-01 | 2027-03-01 | Falls | NORTH | SS Completed, FIS Started, No IA
Kruth Storage | Martinez Energy Storage LLC | 203 | 2026-03-01 | 2027-03-01 | Angelina | NORTH | SS Completed, FIS Started, No IA
Duffy BESS | Duffy Energy Storage LLC | 235.7 | 2026-03-01 | 2027-03-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Quantum Storage | IP Quantum II, LLC | 321.06 | 2026-03-01 | 2027-03-01 | Haskell | WEST | SS Started, FIS Started, No IA
High Noon Storage | High Noon Solar Project, LLC | 94 | 2026-04-01 | 2027-04-01 | Hill | NORTH | SS Completed, FIS Started, No IA
HGP Pacesetter BESS | HGP Storage, LLC | 200.83 | 2026-04-01 | 2027-04-01 | Dallas | NORTH | SS Completed, FIS Completed, No IA
Sandman Power Storage | ALPIN HOLDING LLC | 100 | 2026-04-01 | 2027-04-01 | Collin | NORTH | SS Completed, FIS Started, No IA
Cadet Storage | TX BESS 5, LLC | 104.42 | 2026-04-01 | 2027-04-01 | Brazos | NORTH | SS Completed, FIS Started, No IA
Emerald Hill Energy Storage | Emerald Hill Energy Storage LLC | 261.02 | 2026-04-01 | 2027-04-01 | Dallas | NORTH | SS Completed, FIS Started, No IA
Fort Chadbourne Cattle BESS | Fort Chadbourne BESS | 50.23 | 2026-04-01 | 2027-04-01 | Coke | WEST | SS Completed, FIS Started, No IA
Mountain Springs BESS | Mountain Springs BESS | 150.52 | 2026-04-01 | 2027-04-01 | Cooke | NORTH | SS Completed, FIS Started, No IA
Dunkel BESS | Momentum Energy Storage Partners | 225 | 2026-04-01 | 2027-04-01 | Lubbock | PANHANDLE | SS Completed, FIS Started, No IA
Blanket Ranch South Storage SLF | Blanket Ranch South Solar, LLC | 33.8 | 2026-04-01 | 2027-04-01 | Brown | NORTH | SS Completed, FIS Started, No IA
Blanket Ranch North Storage SLF | Blanket Ranch North Solar, LLC | 50.1 | 2026-04-01 | 2027-04-01 | Brown | NORTH | SS Completed, FIS Started, No IA
Blackcat Storage | Matagorda ESS, LLC | 200.59 | 2026-04-01 | 2027-04-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Voyager Storage | EDF Renewables Development, Inc. | 50.14 | 2026-04-01 | 2027-04-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Barton Bishop BESS | Jack Barton BESS LLC | 47.34 | 2026-04-01 | 2027-04-01 | Jack | NORTH | SS Completed, FIS Completed, No IA
Trinity Hills BESS SLF | Phoenix Battery Storage, LLC | 27 | 2026-04-01 | 2027-04-01 | Archer | WEST | SS Completed, FIS Started, No IA
Echols Creek Storage | BT Ferguson Solar, LLC | 100.57 | 2026-04-01 | 2027-04-01 | Lamar | NORTH | SS Completed, FIS Started, No IA
Hynes Bay Energy Storage | Hynes Bay Energy Storage, LLC | 101.2 | 2026-04-01 | 2027-04-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Umbra (Stockyard) BESS | Stockyard Solar Project, LLC | 72.98 | 2026-04-01 | 2027-04-01 | Franklin | NORTH | SS Completed, FIS Completed, IA
Solar Star North Herty Storage | Solar Star North Herty Storage, LLC | 125.4 | 2026-04-01 | 2027-04-01 | Angelina | NORTH | SS Completed, FIS Completed, No IA
Sierra Diablo Energy Storage | SIERRA DIABLO ENERGY STORAGE LLC | 203.81 | 2026-04-01 | 2027-04-01 | Van Zandt | NORTH | SS Completed, FIS Started, No IA
Piedra BESS | Piedra Solar, LLC | 100.4 | 2026-04-01 | 2027-04-01 | Freestone | NORTH | SS Completed, FIS Completed, No IA
Farrier Station Energy Storage | Farrier Station Energy Storage Project, LLC | 409.9 | 2026-04-01 | 2027-04-01 | Hopkins | NORTH | SS Completed, FIS Started, No IA
Dolce BESS | Dolce BESS, LLC | 100.65 | 2026-04-01 | 2027-04-01 | Mitchell | WEST | SS Completed, FIS Started, No IA
Seragio BESS | Seragio BESS, LLC | 201.13 | 2026-04-01 | 2027-04-01 | Ector | WEST | SS Completed, FIS Started, No IA
Dionysus Storage | Dionysus Solar, LLC | 77.28 | 2026-04-01 | 2027-04-01 | Houston | NORTH | SS Completed, FIS Started, No IA
Palladium Storage | Palladium Energy Storage LLC | 152 | 2026-04-01 | 2027-04-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Lager Storage | Momentum Energy Storage Partners,LLC | 30 | 2026-04-01 | 2027-04-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Guinness BESS | Momentum Energy Storage Partners,LLC | 100.51 | 2026-04-01 | 2027-04-01 | Williamson | SOUTH | SS Completed, FIS Started, No IA
PaleAle BESS | Momentum Energy Storage Partners,LLC | 75.38 | 2026-04-01 | 2027-04-01 | Hays | SOUTH | SS Completed, FIS Started, No IA
Pruett Storage | Crandall Solar LLC | 50.48 | 2026-04-01 | 2027-04-01 | Wise | NORTH | SS Completed, FIS Started, No IA
Kahla Storage | BT Kahla Storage, LLC | 200.9 | 2026-04-01 | 2027-04-01 | Leon | NORTH | SS Completed, FIS Started, No IA
Tidwell Prairie III Batt | Tidwell Prairie LLC | 200 | 2026-05-01 | 2027-05-01 | Robertson | NORTH | SS Completed, FIS Started, No IA
Louisa Energy Storage | Viridity Energy Solutions Inc. | 102.77 | 2026-05-01 | 2027-05-01 | Bexar | SOUTH | SS Completed, FIS Completed, No IA
East West BESS | Black Mountain Energy Storage II, LLC | 100.8 | 2026-05-01 | 2027-05-01 | Kerr | SOUTH | SS Completed, FIS Started, No IA
Railway BESS | Grand Reserve Energy, LLC | 254.8 | 2026-05-01 | 2027-05-01 | Rusk | NORTH | SS Completed, FIS Started, No IA
TOCE BESS 1 | TOCE BESS 1, LLC | 205.2 | 2026-05-01 | 2027-05-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Marick Rose BESS | Marick BESS | 50.18 | 2026-05-01 | 2027-05-01 | Fort Bend | HOUSTON | SS Completed, FIS Completed, No IA
ALWEST BESS | Castleman Power | 208.63 | 2026-05-01 | 2027-05-01 | Anderson | NORTH | SS Completed, FIS Started, No IA
Hofbrau BESS | Momentum Energy Storage Partners, LLC | 180.72 | 2026-05-01 | 2027-05-01 | Tom Green | WEST | SS Completed, FIS Started, No IA
Larkspur Energy Storage | Larkspur Energy Storage LLC | 307.46 | 2026-05-01 | 2027-05-01 | Upton | WEST | SS Completed, FIS Started, IA
Sigma Storage | AES Distributed Energy, Inc | 408.4 | 2026-05-01 | 2027-05-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Beacon Storage | AES Distributed Energy, Inc | 408.7 | 2026-05-01 | 2027-05-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Best Southwest BESS | North Texas Energy Storage LLC | 241.44 | 2026-05-01 | 2027-05-01 | Dallas | NORTH | SS Completed, FIS Completed, No IA
GAMAY ENERGY STORAGE | GAMAY ENERGY STORAGE LLC | 418.6 | 2026-05-01 | 2027-05-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Seven Springs Storage | Hancock Reservoir, LLC | 170.51 | 2026-05-01 | 2027-05-01 | Lampasas | NORTH | SS Started, FIS Started, No IA
Capoterra BESS | 206OF 8me LLC | 600 | 2026-05-01 | 2027-05-01 | Milam | SOUTH | SS Completed, FIS Started, No IA
AQUAMARINE BESS | ME USA Project I LLC | 213.81 | 2026-05-01 | 2027-05-01 | Dickens | PANHANDLE | SS Completed, FIS Started, No IA
McGee Storage | BT McGee Storage, LLC | 151.39 | 2026-05-01 | 2027-05-01 | Henderson | NORTH | SS Completed, FIS Started, No IA
Yooperlite Storage | BT Yooperlite Storage, LLC | 175.65 | 2026-05-01 | 2027-05-01 | Wise | NORTH | SS Completed, FIS Started, No IA
Upstream BESS | Upstream Storage LLC | 461.6 | 2026-05-01 | 2027-05-01 | Johnson | NORTH | SS Completed, FIS Started, No IA
Green Holly Storage | GreenGo Energy | 50 | 2026-05-01 | 2027-05-01 | Dawson | WEST | SS Completed, FIS Started, IA
Red Holly Storage | GreenGo Energy | 50 | 2026-05-01 | 2027-05-01 | Dawson | WEST | SS Completed, FIS Started, IA
Nautilus Heavy Storage | Nautilus Heavy Storage, LLC | 511.9 | 2026-05-01 | 2027-05-01 | San Patricio | COASTAL | SS Completed, FIS Started, No IA
Ferdinand Grid BESS | Ferdinand Grid, LLC | 202.65 | 2026-05-01 | 2027-05-01 | Bexar | SOUTH | SS Completed, FIS Started, IA
Carambola BESS | SMT McAllen II LLC | 97.43 | 2026-05-01 | 2027-05-01 | Hidalgo | SOUTH | SS Completed, FIS Started, IA
Macho Creek BESS | Macho Creek BESS, LLC | 150.56 | 2026-05-01 | 2027-05-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
Fairway Storage | Fairway Storage LLC | 121.03 | 2026-05-01 | 2027-05-01 | Freestone | NORTH | SS Completed, FIS Started, No IA
Charro Creek Storage 1 SLF | Charro Creek Solar LLC | 0 | 2026-05-01 | 2027-05-01 | Karnes | SOUTH | SS Completed, FIS Started, No IA
Charro Creek Storage 2 SLF | Charro Creek Solar LLC | 0 | 2026-05-01 | 2027-05-01 | Karnes | SOUTH | SS Completed, FIS Started, No IA
Charro Creek Storage 3 SLF | Charro Creek Solar LLC | 0 | 2026-05-01 | 2027-05-01 | Karnes | SOUTH | SS Completed, FIS Started, No IA
Freedom Falcon BESS | Falcon BESS, LLC | 501.9 | 2026-05-01 | 2027-05-01 | Zapata | SOUTH | SS Completed, FIS Started, No IA
Falcon Zapata Storage 138 | Falcon BESS, LLC | 200.79 | 2026-05-01 | 2027-05-01 | Zapata | SOUTH | SS Completed, FIS Started, No IA
BRP Octans BESS | BRP OCTANS BESS LLC | 129.57 | 2026-06-01 | 2027-06-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Pajarita BESS | VESI 29 LLC | 205.5 | 2026-06-01 | 2027-06-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
St. Gall II Energy Storage | St. Gall Energy Storage LLC | 102.6 | 2026-06-01 | 2027-06-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Lavender Storage Project | Lavender Storage Project LLC | 231.9 | 2026-06-01 | 2027-06-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
Taormina Storage | Taormina Storage Project LLC | 231.86 | 2026-06-01 | 2027-06-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
Burro Loco Energy Storage | VESI | 25.14 | 2026-06-01 | 2027-06-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Mystic Springs Renewable Energy Storage SLF | Tawakoni Park Storage LLC | 0 | 2026-06-01 | 2027-06-01 | Kaufman | NORTH | SS Completed, FIS Started, No IA
Anatole Renewable Energy Storage | Eustace Storage LLC | 207.82 | 2026-06-01 | 2027-06-01 | Henderson | NORTH | SS Completed, FIS Completed, No IA
Hornet Storage II SLF | Hornet Storage II LLC | 0 | 2026-06-01 | 2027-06-01 | Castro | PANHANDLE | SS Completed, FIS Started, No IA
Bracero Pecan Storage | Bracero Pecan Storage LLC | 232 | 2026-06-01 | 2027-06-01 | Reeves | WEST | SS Completed, FIS Started, No IA
Jane Storage Energy Center | NMRE Holdings, LLC | 240.6 | 2026-06-01 | 2027-06-01 | Martin | WEST | SS Completed, FIS Started, No IA
Wadsworth Storage Energy Center | Nova Clean Energy Real Estate, LLC | 200.8 | 2026-06-01 | 2027-06-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Buffalo Creek BESS | Orsted Onshore North America LLC | 256.68 | 2026-06-01 | 2027-06-01 | Fort Bend | HOUSTON | SS Started, FIS Started, No IA
BremRaek BESS | BremRaek BESS | 200.6 | 2026-06-01 | 2027-06-01 | Austin | SOUTH | SS Started, FIS Started, No IA
Bologna BESS | MALONEY BESS LLC | 202.56 | 2026-06-01 | 2027-06-01 | Wichita | WEST | SS Started, FIS Started, No IA
Ochoa Energy Storage II | Ochoa Energy Storage II LLC | 501.72 | 2026-06-01 | 2027-06-01 | Waller | HOUSTON | SS Started, FIS Started, No IA
Hacienda Storage | Galveston Energy Storage LLC | 209.14 | 2026-06-01 | 2027-06-01 | Galveston | HOUSTON | SS Completed, FIS Started, No IA
Aggie Energy storage | KINGFISHER ENERGY STORAGE LLC | 104.4 | 2026-06-01 | 2027-06-01 | Brazos | NORTH | SS Completed, FIS Started, No IA
Oriana BESS | Oriana Solar LLC | 60.3 | 2026-06-01 | 2027-06-01 | Victoria | SOUTH | SS Completed, FIS Started, IA
Southside Energy | Southside Energy, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Battlefield Energy | Battlefield Energy, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Parthenon Energy | Parthenon Energy, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Nerva Energy Storage | Nerva Energy Storage, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Hadrian Energy Storage | Hadrian Energy Storage, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Antoninus Energy Storage | Antoninus Energy Storage, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Port City Energy Storage | Port City Energy Storage, LLC | 101.2 | 2026-06-01 | 2027-06-01 | San Patricio | COASTAL | SS Completed, FIS Started, No IA
Palacios Bay Energy Storage | Palacios Bay Energy Storage, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Blue Creek Energy Storage | Blue Creek Energy Storage, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Copano Bay Energy Storage | Copano Bay Energy Storage, LLC | 101.2 | 2026-06-01 | 2027-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Country Haven Energy Storage | 174 Power Global Properties, LLC | 72.05 | 2026-06-01 | 2027-06-01 | Rains | NORTH | SS Completed, FIS Completed, No IA
Forts Trail BESS | JC Central Bluff, LLC | 200.93 | 2026-06-01 | 2027-06-01 | Taylor | WEST | SS Completed, FIS Started, No IA
Forts Trail BESS 2 | JC Central Bluff, LLC | 201.2 | 2026-06-01 | 2027-06-01 | Taylor | WEST | SS Completed, FIS Completed, No IA
Oyster Creek Storage I SLF | Oyster Creek Solar 1, LLC | 0 | 2026-06-01 | 2027-06-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Borderland ESC | FRESH AIR ENERGY II, LLC | 200 | 2026-06-01 | 2027-06-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Evans Creek Energy Storage | Evans Creek Energy Storage LLC | 102.96 | 2026-06-01 | 2027-06-01 | Val Verde | WEST | SS Completed, FIS Started, No IA
Lightning Ridge Energy Storage | Lightning Ridge Storage LLC | 200.8 | 2026-06-01 | 2027-06-01 | Jack | NORTH | SS Started, FIS Started, No IA
Mercury Storage | Mercury Storage, LLC | 0 | 2026-07-01 | 2027-07-01 | Hill | NORTH | SS Completed, FIS Started, No IA
Flagtail BESS | Flagtail LLC | 203.8 | 2026-07-01 | 2027-07-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
Lumberjack Storage | EDP Renewables North America LLC | 51.3 | 2026-07-01 | 2027-07-01 | Cherokee | NORTH | SS Completed, FIS Completed, IA
BRP Snowdon BESS | BRP SNOWDON BESS LLC | 410.94 | 2026-07-01 | 2027-07-01 | Briscoe | PANHANDLE | SS Completed, FIS Started, No IA
BRP Hemera BESS | BRP Hemera BESS LLC | 206.96 | 2026-07-01 | 2027-07-01 | Deaf Smith | PANHANDLE | SS Completed, FIS Started, No IA
Lacy Creek BESS SLF | Edmondson Ranch Wind Holdings, LLC | 0 | 2026-07-01 | 2027-07-01 | Glasscock | WEST | SS Started, FIS Started, No IA
Thomas Cameron BESS | Thomas Cameron BESS | 200.82 | 2026-07-01 | 2027-07-01 | Lampasas | NORTH | SS Completed, FIS Started, No IA
Argenta Storage | Charter Oak Storage, LLC | 162 | 2026-07-01 | 2027-07-01 | Bee | SOUTH | SS Completed, FIS Started, IA
Violet Storage | VIOLET STORAGE | 151 | 2026-07-01 | 2027-07-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Concho Pearl Storage | Concho Pearl Solar, LLC | 162.4 | 2026-07-01 | 2027-07-01 | Concho | WEST | SS Completed, FIS Started, No IA
OCI SunRoper ESS | OCI SunRoper LLC | 265.6 | 2026-07-01 | 2027-07-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Marshall Spring Storage | Ampyr Energy USA, LLC | 150 | 2026-07-01 | 2027-07-01 | Gillespie | SOUTH | SS Completed, FIS Started, No IA
Blue Summit Energy Storage | NextEra Energy Interconnection Holdings, LLC | 100 | 2026-07-01 | 2027-07-01 | Wilbarger | WEST | SS Completed, FIS Started, No IA
Elm Flats Storage SLF | Elm Flats Solar, LLC | 0 | 2026-07-01 | 2027-07-01 | Navarro | NORTH | SS Completed, FIS Started, No IA
Operation Sunshine Storage | Duck Creek Storage, LLC | 409.5 | 2026-07-01 | 2027-07-01 | Concho | WEST | SS Completed, FIS Started, No IA
Gail Mountain Storage | Gail Mountain Solar, LLC | 152 | 2026-07-01 | 2027-07-01 | Borden | WEST | SS Completed, FIS Started, No IA
Anila BESS | Alina Energy LLC | 209 | 2026-07-01 | 2027-07-01 | Wilson | SOUTH | SS Completed, FIS Started, No IA
Rock Rose Energy BESS | Rock Rose Energy LLC | 211.5 | 2026-07-01 | 2027-07-01 | Fort Bend | HOUSTON | SS Completed, FIS Started, No IA
Bluewind Energy Center | Bluewind Energy Center, LLC | 102.56 | 2026-07-01 | 2027-07-01 | Atascosa | SOUTH | SS Started, FIS Started, No IA
Vial BESS | Gransolar Texas Eleven LLC | 141.39 | 2026-07-01 | 2027-07-01 | Hill | NORTH | SS Completed, FIS Started, No IA
Rock N' Roll Storage SLF | Rock N' Roll Solar, LLC | 0 | 2026-07-01 | 2027-07-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Rock N' Roll Storage Two | Rock N' Roll Solar, LLC | 206 | 2026-07-01 | 2027-07-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Saluga Ranch Storage | Saluga Ranch Energy, LLC | 105.98 | 2026-07-01 | 2027-07-01 | Dimmit | SOUTH | SS Completed, FIS Started, No IA
Hiru Storage | Hecate Energy Hazel LLC | 503.8 | 2026-08-01 | 2027-08-01 | Clay | WEST | SS Completed, FIS Started, No IA
Inadale BESS | Inadale BESS, LLC | 286.66 | 2026-08-01 | 2027-08-01 | Scurry | WEST | SS Completed, FIS Started, No IA
Staked Plains BESS | Grand Reserve Energy, LLC | 254.8 | 2026-08-01 | 2027-08-01 | Lubbock | PANHANDLE | SS Completed, FIS Started, No IA
Bonaparte BESS | Bonaparte BESS, LLC | 153.67 | 2026-08-01 | 2027-08-01 | Lee | SOUTH | SS Completed, FIS Started, No IA
Wallie Storage | Wallie Storage, LLC | 205.4 | 2026-08-01 | 2027-08-01 | Howard | WEST | SS Completed, FIS Started, No IA
Brackens BESS | Brackens BESS | 103.58 | 2026-08-01 | 2027-08-01 | Freestone | NORTH | SS Completed, FIS Started, No IA
Harlingen III BESS | SMT Harlingen III LLC | 110 | 2026-08-01 | 2027-08-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Shoshana Storage | Shoshana Storage Project LLC | 221 | 2026-08-01 | 2027-08-01 | Matagorda | COASTAL | SS Completed, FIS Completed, No IA
Ardesia Storage | Ardesia Storage Project LLC | 100 | 2026-08-01 | 2027-08-01 | Caldwell | SOUTH | SS Completed, FIS Started, No IA
Appaloosa Run BESS | Appaloosa Run BESS | 200.5 | 2026-08-01 | 2027-08-01 | Upton | WEST | SS Completed, FIS Started, No IA
PHOTO BESS 1 | CED Development Inc. | 75 | 2026-09-01 | 2027-09-01 | Uvalde | SOUTH | SS Completed, FIS Started, No IA
PHOTO BESS 2 | CED Development Inc. | 150 | 2026-09-01 | 2027-09-01 | Uvalde | SOUTH | SS Completed, FIS Started, No IA
Photo BESS 3 | CED Development Inc. | 100 | 2026-09-01 | 2027-09-01 | Uvalde | SOUTH | SS Completed, FIS Started, No IA
Myers Storage | BT Myers Solar, LLC | 75.7 | 2026-09-01 | 2027-09-01 | Bee | SOUTH | SS Completed, FIS Started, No IA
Megamouth Energy Storage | GCI Megamouth, LLC | 101.3 | 2026-09-01 | 2027-09-01 | Harris | HOUSTON | SS Started, FIS Started, No IA
OCI Cobb Creek ESS | OCI Hillsboro Solar LLC | 201.6 | 2026-09-01 | 2027-09-01 | Hill | NORTH | SS Completed, FIS Started, No IA
Umbra BESS II | Saddle House Solar Project, LLC | 149.64 | 2026-09-01 | 2027-09-01 | Franklin | NORTH | SS Completed, FIS Started, No IA
Claxton Storage | BT Claxton Solar, LLC | 75.7 | 2026-09-01 | 2027-09-01 | Hopkins | NORTH | SS Completed, FIS Started, No IA
Willis Storage | BT Willis Storage, LLC | 176.13 | 2026-09-01 | 2027-09-01 | Rains | NORTH | SS Completed, FIS Started, No IA
McMurtre Storage | BT McMurtre Storage, LLC | 176.13 | 2026-09-01 | 2027-09-01 | Hunt | NORTH | SS Completed, FIS Started, No IA
Opuntia Storage SLF | Opuntia Solar, LLC | 0 | 2026-09-01 | 2027-09-01 | Refugio | COASTAL | SS Completed, FIS Started, No IA
Brantley Branch Batt | Brantley Branch LLC | 302.35 | 2026-09-01 | 2027-09-01 | Rusk | NORTH | SS Completed, FIS Started, No IA
Champaign BESS | Champaign BESS, LLC | 201.13 | 2026-09-01 | 2027-09-01 | Glasscock | WEST | SS Completed, FIS Started, No IA
Fairgreen BESS | Fairgreen BESS, LLC | 201.13 | 2026-09-01 | 2027-09-01 | Howard | WEST | SS Completed, FIS Started, No IA
Sagewood BESS | Sagewood BESS, LLC | 100.57 | 2026-09-01 | 2027-09-01 | Glasscock | WEST | SS Completed, FIS Started, No IA
Ariji BESS | Ariji BESS, LLC | 100.32 | 2026-09-01 | 2027-09-01 | Howard | WEST | SS Completed, FIS Started, No IA
Jasper BESS | Jasper BESS, LLC | 201.13 | 2026-09-01 | 2027-09-01 | Midland | WEST | SS Completed, FIS Started, No IA
Blue Heron BESS | Blue Heron BESS, LLC | 201.08 | 2026-09-01 | 2027-09-01 | Reeves | WEST | SS Completed, FIS Started, No IA
Star Dairy Storage | Star Dairy Storage | 204.93 | 2026-09-01 | 2027-09-01 | Lamar | NORTH | SS Completed, FIS Started, No IA
Happy Dog Storage | Rosula Solar LLC | 60.16 | 2026-09-01 | 2027-09-01 | Milam | SOUTH | SS Completed, FIS Started, No IA
Castle Corral BESS | Castle Corral BESS, LLC | 200.9 | 2026-09-01 | 2027-09-01 | Mills | NORTH | SS Completed, FIS Started, No IA
JackGard BESS | Jackgard BESS | 200.59 | 2026-09-01 | 2027-09-01 | Jack | NORTH | SS Completed, FIS Started, No IA
Fort Watt Storage | Fort Watt Storage, LLC | 201.4 | 2026-09-01 | 2027-09-01 | Tarrant | NORTH | SS Completed, FIS Started, No IA
Roost Energy Storage | Bluff Creek Energy Storage LLC | 102.36 | 2026-09-01 | 2027-09-01 | Scurry | WEST | SS Completed, FIS Started, No IA
Wetzel BESS | Brown ESS, LLC | 185.57 | 2026-09-01 | 2027-09-01 | Brown | NORTH | SS Completed, FIS Started, No IA
Stewart Grady BESS | Grady BESS | 150.5 | 2026-09-01 | 2027-09-01 | Martin | WEST | SS Completed, FIS Started, No IA
Rogers Creek BESS | Dialville BESS | 100.33 | 2026-09-01 | 2027-09-01 | Cherokee | NORTH | SS Completed, FIS Started, No IA
Acker BESS | Ogallala BESS LLC | 301.04 | 2026-09-01 | 2027-09-01 | Castro | PANHANDLE | SS Completed, FIS Started, No IA
Soleil Storage | Soleil Solar, LLC | 301.64 | 2026-09-01 | 2027-09-01 | Clay | WEST | SS Completed, FIS Completed, No IA
Lupinus Storage 1 | Lupinus Solar, LLC | 82.97 | 2026-09-01 | 2027-09-01 | Franklin | NORTH | SS Completed, FIS Started, No IA
Lupinus Storage 2 | Lupinus Solar 2, LLC | 122.92 | 2026-09-01 | 2027-09-01 | Franklin | NORTH | SS Completed, FIS Started, No IA
Lupinus Storage 3 | Lupinus Solar 2, LLC | 50.9 | 2026-09-01 | 2027-09-01 | Franklin | NORTH | SS Completed, FIS Started, No IA
Millennium Energy Storage | Rocky Mountain Energy Development, LLC | 102.59 | 2026-09-01 | 2027-09-01 | Martin | WEST | SS Completed, FIS Started, No IA
Tyler BESS | SMT Tyler LLC | 305.3 | 2026-09-01 | 2027-09-01 | Smith | NORTH | SS Completed, FIS Started, No IA
Timberline Storage | Timberline Renewables, LLC | 100.5 | 2026-09-01 | 2027-09-01 | Nacogdoches | NORTH | SS Completed, FIS Started, No IA
Cape Rich BESS | Cape Rich BESS | 150.52 | 2026-09-01 | 2027-09-01 | Navarro | NORTH | SS Completed, FIS Started, No IA
RIVERBEND STORAGE SLF | Riverbend Renewables, LLC | 0 | 2026-09-01 | 2027-09-01 | Falls | NORTH | SS Completed, FIS Started, No IA
Proteus Thornton Ranch Storage SLF | Thornton Ranch Solar, LLC | 0 | 2026-09-01 | 2027-09-01 | Ward | WEST | SS Started, FIS Started, No IA
Apis Storage | S&S Renewables LLC | 268.43 | 2026-09-01 | 2027-09-01 | Bee | SOUTH | SS Completed, FIS Started, No IA
Solace Storage | IP Quantum, LLC | 321.02 | 2026-09-01 | 2027-09-01 | Haskell | WEST | SS Started, FIS Started, No IA
Goldhill Energy Storage | Goldhill Energy Storage LLC | 200.58 | 2026-09-01 | 2027-09-01 | Victoria | SOUTH | SS Started, FIS Started, No IA
Bluegill BESS | Bluegill BESS | 501.9 | 2026-10-01 | 2027-10-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Bramble Energy Center | Mission Clean Energy LLC | 225.1 | 2026-10-01 | 2027-10-01 | Zavala | SOUTH | SS Completed, FIS Started, No IA
Chisme Storage | Blue Heron Solar, LLC | 146 | 2026-10-01 | 2027-10-01 | Brown | NORTH | SS Completed, FIS Started, No IA
Wolf Spring Storage | Wolf Spring Solar, LLC | 202.7 | 2026-10-01 | 2027-10-01 | Dickens | PANHANDLE | SS Completed, FIS Started, No IA
Neutron Storage | Neutron Storage | 104.36 | 2026-10-01 | 2027-10-01 | McLennan | NORTH | SS Completed, FIS Started, No IA
Amerada Storage | Amerada Solar, LLC | 150.78 | 2026-10-01 | 2027-10-01 | Freestone | NORTH | SS Completed, FIS Started, No IA
Possum Kingdom BESS | Novis Renewables, LLC | 201.33 | 2026-10-01 | 2027-10-01 | Jack | NORTH | SS Completed, FIS Started, No IA
Ranchero BESS | Ranchero Battery Facility, LLC | 150 | 2026-10-01 | 2027-10-01 | Crockett | WEST | SS Completed, FIS Started, No IA
Riverwalk BESS | CED Development Inc. | 120 | 2026-10-01 | 2027-10-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
Senator Aggreko Storage | Senator Aggreko Storage LLC | 153.1 | 2026-10-01 | 2027-10-01 | Maverick | SOUTH | SS Completed, FIS Started, No IA
Butterfield Energy Storage | Butterfield Energy Storage LLC | 207.6 | 2026-11-01 | 2027-11-01 | Jack | NORTH | SS Completed, FIS Started, No IA
Bayside 2 BESS | Bayside 2 BESS | 252.3 | 2026-11-01 | 2027-11-01 | DeWitt | SOUTH | SS Completed, FIS Started, No IA
LARISA BESS | ME USA PROJECT II LLC | 418.49 | 2026-11-01 | 2027-11-01 | Jones | WEST | SS Completed, FIS Started, No IA
Bessie Storage | Deriva Energy Storage, LLC | 210.8 | 2026-11-01 | 2027-11-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
Apache Hill BESS | Black Mountain Energy Storage II | 201.2 | 2026-11-01 | 2027-11-01 | Hood | NORTH | SS Completed, FIS Started, No IA
Galactic Storage SLF | UKA North America, LLC | 0 | 2026-11-01 | 2027-11-01 | Grayson | NORTH | SS Completed, FIS Started, No IA
Furay Battery Energy Storage System | Blue Topaz 1, LLC | 304 | 2026-11-01 | 2027-11-01 | Harris | HOUSTON | SS Completed, FIS Completed, No IA
Blossomheath BESS | Taurbeng LLC | 300.78 | 2026-11-01 | 2027-11-01 | Ellis | NORTH | SS Completed, FIS Started, No IA
Augie BESS | BRP Blue Topaz 5, LLC | 200.81 | 2026-11-01 | 2027-11-01 | Waller | HOUSTON | SS Completed, FIS Completed, No IA
Claire BESS | BRP Blue Topaz 3, LLC | 406.01 | 2026-11-01 | 2027-11-01 | Harris | HOUSTON | SS Completed, FIS Completed, No IA
Smith Lake Storage | Smith Lake Solar | 65 | 2026-11-01 | 2027-11-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
Blue Bird BESS | Gigawatt Solar LLC | 200.7 | 2026-11-01 | 2027-11-01 | Hood | NORTH | SS Completed, FIS Started, No IA
Venture Hill Storage | KCE TX 24, LLC | 70.44 | 2026-12-01 | 2027-12-01 | Travis | SOUTH | SS Completed, FIS Started, No IA
Bottom Grass BESS | Bottom Grass Solar Project, LLC | 202.21 | 2026-12-01 | 2027-12-01 | Colorado | SOUTH | SS Completed, FIS Started, IA
BRP Pollux BESS | BRP Pollux BESS LLC | 163.42 | 2026-12-01 | 2027-12-01 | Bosque | NORTH | SS Completed, FIS Started, No IA
BRP Triton BESS | BRP Triton BESS LLC | 205.36 | 2026-12-01 | 2027-12-01 | Comanche | NORTH | SS Completed, FIS Started, No IA
Two Brothers Battery Energy Storage System | Blue Topaz 2, LLC | 152 | 2026-12-01 | 2027-12-01 | Victoria | SOUTH | SS Completed, FIS Started, IA
Serrano Storage | Maverick ESS, LLC | 185.59 | 2026-12-01 | 2027-12-01 | Maverick | SOUTH | SS Completed, FIS Started, No IA
McMEXICO STORAGE | FRESH AIR ENERGY II, LLC | 201.9 | 2026-12-01 | 2027-12-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Bottom Grass BESS II | Flint Rock Solar Project, LLC | 150.6 | 2026-12-01 | 2027-12-01 | Colorado | SOUTH | SS Completed, FIS Started, No IA
IEP Blackhawk | IEP Texas Verde II, llc | 100 | 2026-12-01 | 2027-12-01 | Galveston | HOUSTON | SS Completed, FIS Started, No IA
Dolomite Storage | BT Wilson Storage, LLC | 125.7 | 2026-12-01 | 2027-12-01 | Ellis | NORTH | SS Completed, FIS Started, No IA
Adam Bryant BESS | Adam Bryant BESS LLC | 99.9 | 2026-12-01 | 2027-12-01 | Medina | SOUTH | SS Started, FIS Started, No IA
Becerra Creek Storage 1 | Bordas Renewable Energy, LLC | 125.62 | 2026-12-01 | 2027-12-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
Hill Valley BESS | Hill Valley BESS, LLC | 245.8 | 2026-12-01 | 2027-12-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
Misty Hollow BESS | Clear Fork BESS, LLC | 245.8 | 2026-12-01 | 2027-12-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
Avalon BESS | Greenbelt ERCOT BESS Holdings, LLC | 522.12 | 2026-12-01 | 2027-12-01 | Fort Bend | HOUSTON | SS Completed, FIS Started, No IA
Rock Creek BESS | Flat Rock Energy Center, LLC | 251.05 | 2026-12-01 | 2027-12-01 | Kendall | SOUTH | SS Started, FIS Started, No IA
Sorghum BESS | Greenbelt ERCOT BESS Holdings, LLC | 208.9 | 2026-12-01 | 2027-12-01 | Wharton | SOUTH | SS Started, FIS Started, No IA
Elio BESS | Elio Energy LLC | 317.2 | 2026-12-01 | 2027-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Alexandrite Storage | Johnson Energy Storage, LLC | 203 | 2026-12-01 | 2027-12-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Frye Storage | Hecate Energy Frye Storage LLC | 510 | 2026-12-01 | 2027-12-01 | Swisher | PANHANDLE | SS Completed, FIS Started, No IA
Charolais Storage | RWE Solar Development, LLC | 150 | 2026-12-01 | 2027-12-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Yorktown BESS | Navitas Energy LLC | 150.49 | 2026-12-01 | 2027-12-01 | DeWitt | SOUTH | SS Completed, FIS Started, No IA
Larimar Storage | BT S7 Solar, LLC | 100.91 | 2026-12-01 | 2027-12-01 | Bee | SOUTH | SS Completed, FIS Started, No IA
Olsovksy Storage | BT Sky Storage, LLC | 151.42 | 2026-12-01 | 2027-12-01 | Hill | NORTH | SS Completed, FIS Started, No IA
Backbone Creek BESS | Backbone Creek BESS LLC | 120.69 | 2026-12-01 | 2027-12-01 | Burnet | SOUTH | SS Completed, FIS Started, IA
Cuchillas BESS | Gransolar Texas Two | 306.94 | 2026-12-01 | 2027-12-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
Equinox Storage | Invenergy Storage Development LLC | 101.2 | 2026-12-01 | 2027-12-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
Kobernat Storage | BT Kobernat Solar, LLC | 51.46 | 2026-12-01 | 2027-12-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
Kota Battery | Kota Storage, LLC | 200.6 | 2026-12-01 | 2027-12-01 | Carson | PANHANDLE | SS Completed, FIS Started, No IA
Flag City Storage SLF | Flag City Solar Project, LLC | 0 | 2026-12-01 | 2027-12-01 | Jackson | SOUTH | SS Completed, FIS Completed, No IA
Pisgah Ridge Storage 3 | Pisgah Ridge 3, LLC | 101.36 | 2026-12-01 | 2027-12-01 | Navarro | NORTH | SS Completed, FIS Completed, No IA
Merchant BESS | Merchant BESS LLC | 201.2 | 2026-12-01 | 2027-12-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Brushwood Energy Storage | Flagtail LLC | 203.78 | 2026-12-01 | 2027-12-01 | Grimes | NORTH | SS Completed, FIS Completed, No IA
ELECTRODE BESS | CED Development Inc. | 150 | 2026-12-01 | 2027-12-01 | Upton | WEST | SS Completed, FIS Started, No IA
CATHODE BESS | CED Development Inc. | 150 | 2026-12-01 | 2027-12-01 | Upton | WEST | SS Completed, FIS Started, No IA
Portside Energy Center (BESS) SLF | Portside Energy Center, LLC | 41.42 | 2026-12-01 | 2027-12-01 | Victoria | SOUTH | SS Completed, FIS Started, IA
Hollow Branch Creek Storage | Hollow Branch Creek Solar LLC | 460 | 2026-12-01 | 2027-12-01 | Leon | NORTH | SS Completed, FIS Started, No IA
PSE Flores TX Storage | PureSky Development Inc | 200 | 2026-12-01 | 2027-12-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
PSE Gongora Hill TX Storage | PureSky Development Inc | 200 | 2026-12-01 | 2027-12-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
PSE Chihuahua TX Storage | PureSky Development Inc | 200 | 2026-12-01 | 2027-12-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
PSE Minnesota TX Storage | PureSky Development Inc | 100 | 2026-12-01 | 2027-12-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
PSE Richardson TX Storage | PureSky Development Inc. | 100 | 2026-12-01 | 2027-12-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Proteus Vernon Storage SLF | Vernon Solar and Storage LLC (a Delaware LLC) | 0 | 2026-12-01 | 2027-12-01 | Wilbarger | WEST | SS Completed, FIS Started, No IA
Surfside Energy Storage | Rocky Mountain Energy Holdings, LLC | 50.34 | 2026-12-01 | 2027-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Old Sorrell Energy Storage | Rocky Mountain Energy Holdings, LLC | 43.1 | 2026-12-01 | 2027-12-01 | Concho | WEST | SS Completed, FIS Started, No IA
Stegall Storage | BT Martin Solar, LLC | 50.47 | 2026-12-01 | 2027-12-01 | Robertson | NORTH | SS Completed, FIS Started, No IA
LUND STORAGE CENTER 1 | Lund Storage Center 1, LLC | 407.55 | 2026-12-01 | 2027-12-01 | Bastrop | SOUTH | SS Completed, FIS Started, No IA
Weathervane Storage SLF | Mallard Place LLC | 32.47 | 2026-12-01 | 2027-12-01 | Montague | NORTH | SS Completed, FIS Started, No IA
DMF Sagerton Storage SLF | Double Mountain Fork LLC | 0 | 2026-12-01 | 2027-12-01 | Haskell | WEST | SS Completed, FIS Started, No IA
Realitos Storage SLF | Mesquite Creek LLC | 0 | 2026-12-01 | 2027-12-01 | Duval | SOUTH | SS Completed, FIS Started, No IA
Firebird BESS | TX BESS 6, LLC | 100.42 | 2026-12-01 | 2027-12-01 | Ector | WEST | SS Completed, FIS Started, No IA
Cold Creek Storage 2 | Cold Creek Solar LLC | 174.24 | 2026-12-01 | 2027-12-01 | Schleicher | WEST | SS Completed, FIS Started, No IA
Windmill Ridge Storage | BT WMR Storage, LLC | 151.4 | 2026-12-01 | 2027-12-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
AGGIE STORAGE PROJECT SLF | reNRG TX 8 LLC | 0 | 2026-12-01 | 2027-12-01 | Reeves | WEST | SS Completed, FIS Started, No IA
Big Rooter West Storage SLF | Big Rooter West, LLC | 0 | 2026-12-01 | 2027-12-01 | Robertson | NORTH | SS Started, FIS Started, No IA
Cumbia Energy Center | Mission Clean Energy LLC | 200 | 2026-12-01 | 2027-12-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Padua Grid BESS Unit 3 | Padua Grid, LLC | 201.15 | 2026-12-01 | 2027-12-01 | Bexar | SOUTH | SS Started, FIS Started, No IA
Laurel Storage Energy Center | Laurel Energy Center, LLC | 200.8 | 2027-01-01 | 2028-01-01 | Pecos | WEST | SS Completed, FIS Started, No IA
XE Rhoda Storage | Milam 2 Solar LLC | 217.15 | 2027-02-01 | 2028-02-01 | Milam | SOUTH | SS Completed, FIS Started, No IA
Stargazer BESS | Stargazer Solar LLC | 104.5 | 2027-02-01 | 2028-02-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Beaujolais BESS | Beaujolais BESS, LLC | 307.2 | 2027-02-01 | 2028-02-01 | Lamar | NORTH | SS Completed, FIS Started, No IA
Reynolds Park BESS | Iowa Park BESS, LLC | 204.8 | 2027-02-01 | 2028-02-01 | Wichita | WEST | SS Completed, FIS Started, No IA
Silver Spur Energy Center | Silver Spur Energy Center, LLC | 200.83 | 2027-02-01 | 2028-02-01 | Brazos | NORTH | SS Completed, FIS Started, No IA
Lonesome Dove BESS | Hawks BESS, LLC | 256.1 | 2027-02-01 | 2028-02-01 | Throckmorton | WEST | SS Completed, FIS Started, No IA
Nouveau BESS | RamZ BESS, LLC | 256.1 | 2027-02-01 | 2028-02-01 | Throckmorton | WEST | SS Completed, FIS Started, No IA
Sleepy Hollow BESS | Sleepy Hollow BESS, LLC | 123.1 | 2027-02-01 | 2028-02-01 | Throckmorton | WEST | SS Completed, FIS Started, No IA
Hayrick BESS | Gransolar Texas Five LLC | 113.9 | 2027-02-01 | 2028-02-01 | Coke | WEST | SS Completed, FIS Started, No IA
City Breeze BESS | Zenobe City Breeze BESS | 140.6 | 2027-02-01 | 2028-02-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Yellow Rose BESS | Black Mountain Energy Storage II | 201 | 2027-02-01 | 2028-02-01 | Grayson | NORTH | SS Completed, FIS Started, No IA
Two Barbaras BESS | Two Barbaras BESS | 200 | 2027-02-01 | 2028-02-01 | Montgomery | HOUSTON | SS Started, FIS Started, No IA
Oorja Storage | Oorja Storage, LLC | 201.1 | 2027-02-01 | 2028-02-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
Jerboa BESS | Jerboa Storage, LLC | 201.08 | 2027-02-01 | 2028-02-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Langer Storage | Langer Solar, LLC | 61.53 | 2027-03-01 | 2028-03-01 | Bosque | NORTH | SS Completed, FIS Started, No IA
Rio Hondo BESS | SBESS TX25 LLC | 200.78 | 2027-03-01 | 2028-03-01 | Cameron | COASTAL | SS Started, FIS Started, No IA
Atticus Energy Storage | Atticus Energy Storage | 102.98 | 2027-03-01 | 2028-03-01 | Sutton | WEST | SS Started, FIS Started, No IA
Bhalu Storage | Bhalu Storage, LLC | 205.5 | 2027-03-01 | 2028-03-01 | Howard | WEST | SS Completed, FIS Started, No IA
Longday BESS SLF | Longday Solar | 0 | 2027-03-01 | 2028-03-01 | Kinney | SOUTH | SS Completed, FIS Started, No IA
Energy City BESS | Energy City BESS LLC | 204.9 | 2027-03-01 | 2028-03-01 | Midland | WEST | SS Completed, FIS Started, No IA
Eagle Claw Energy Center | Cypress Energy Center, LLC | 200.84 | 2027-03-01 | 2028-03-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
Starlight Storage | Mills Tx Solar LLC | 104.66 | 2027-03-01 | 2028-03-01 | Mills | NORTH | SS Started, FIS Started, No IA
Perry Creek Storage SLF | Perry Creek Solar, LLC | 0 | 2027-03-01 | 2028-03-01 | Freestone | NORTH | SS Completed, FIS Started, No IA
Les Energy Storage | Rocky Mountain Energy Development, LLC | 205.1 | 2027-03-01 | 2028-03-01 | Martin | WEST | SS Completed, FIS Started, No IA
Sandford Storage | BT Sandford Solar, LLC | 100.93 | 2027-03-01 | 2028-03-01 | Wise | NORTH | SS Completed, FIS Started, No IA
Solar Star Rhome Storage | Solar Star Rhome Storage | 220.7 | 2027-03-01 | 2028-03-01 | Wise | NORTH | SS Completed, FIS Started, No IA
Gatsby Energy Storage | Gatsby Energy Storage LLC | 103.36 | 2027-03-01 | 2028-03-01 | Pecos | WEST | SS Completed, FIS Started, No IA
Sugarloaf BESS | Sugarloaf Clean Energy LLC | 100.6 | 2027-03-01 | 2028-03-01 | Dimmit | SOUTH | SS Started, FIS Started, No IA
Timber Cove Storage SLF | Freestone Solar, LLC | 0 | 2027-04-01 | 2028-04-01 | Freestone | NORTH | SS Completed, FIS Started, No IA
Jim Wells ESS | Jim Wells ESS | 100.32 | 2027-04-01 | 2028-04-01 | Jim Wells | SOUTH | SS Started, FIS Started, No IA
Sunlit Pines BESS SLF | Sunlit Pines BESS LLC | 208.12 | 2027-04-01 | 2028-04-01 | Nacogdoches | NORTH | SS Started, FIS Started, No IA
Sodalite Storage | BT DJ4M Solar, LLC | 100.44 | 2027-04-01 | 2028-04-01 | Van Zandt | NORTH | SS Completed, FIS Started, No IA
Malala Storage | Malala Storage, LLC | 205.5 | 2027-04-01 | 2028-04-01 | Dallas | NORTH | SS Completed, FIS Started, No IA
Pethrus BESS | Pethrus BESS, LLC | 174.08 | 2027-04-01 | 2028-04-01 | Wichita | WEST | SS Completed, FIS Started, No IA
Haute Stockage | Haute Stockage, LLC | 307.32 | 2027-04-01 | 2028-04-01 | Shackelford | WEST | SS Completed, FIS Started, No IA
SANJAC BESS | Castleman Power | 202.37 | 2027-04-01 | 2028-04-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Skipjack Energy Storage | Skipper Energy Storage LLC | 150.6 | 2027-04-01 | 2028-04-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Houston County BESS | Houston ESS, LLC | 125.4 | 2027-04-01 | 2028-04-01 | Houston | NORTH | SS Started, FIS Started, No IA
Van Zandt Energy Storage | Rocky Mountain Energy Holdings, LLC | 256.58 | 2027-04-01 | 2028-04-01 | Ector | WEST | SS Completed, FIS Started, No IA
Dovetail Storage | Hecate Energy Dovetail Storage LLC | 508.7 | 2027-04-01 | 2028-04-01 | Jack | NORTH | SS Completed, FIS Started, No IA
Arc Energy Storage | Paris Energy Storage, LLC | 204.5 | 2027-04-01 | 2028-04-01 | Lamar | NORTH | SS Completed, FIS Started, No IA
Firefly Power | Firefly Power LLC | 401.18 | 2027-04-01 | 2028-04-01 | Tarrant | NORTH | SS Started, FIS Started, No IA
Otter BESS | GRS BESS TEXAS TEN, LLC | 157.12 | 2027-04-01 | 2028-04-01 | Bexar | SOUTH | SS Started, FIS Started, No IA
Sol Marina Energy Center BESS | Adapture Solar Development, LLC | 57.15 | 2027-04-01 | 2028-04-01 | Ellis | NORTH | SS Completed, FIS Started, No IA
CORRUSCANT BESS | AEU Battery Project III LLC | 337.35 | 2027-04-01 | 2028-04-01 | Dickens | PANHANDLE | SS Started, FIS Started, No IA
GridGuardian BESS | SMT Temple BESS LLC | 227.99 | 2027-04-01 | 2028-04-01 | Bell | NORTH | SS Completed, FIS Started, No IA
Carolina Storage Odessa | CSE STORAGE, LLC | 203.43 | 2027-04-01 | 2028-04-01 | Howard | WEST | SS Completed, FIS Started, No IA
Cottonseed Energy Storage | Cottonseed Energy Storage LLC | 207.6 | 2027-04-01 | 2028-04-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
Cachena Storage SLF | Clear Fork Creek Solar LLC | 0 | 2027-04-01 | 2028-04-01 | Wilson | SOUTH | SS Completed, FIS Started, No IA
Old Victory Energy Center | Nova Clean Energy LLC | 208.8 | 2027-05-01 | 2028-05-01 | Maverick | SOUTH | SS Started, FIS Started, No IA
REVOLUTION BESS | Nova Clean Energy LLC | 208.8 | 2027-05-01 | 2028-05-01 | La Salle | SOUTH | SS Started, FIS Started, No IA
New Minglewood Energy Center | Nova Clean Energy LLC | 208.8 | 2027-05-01 | 2028-05-01 | Ward | WEST | SS Started, FIS Started, No IA
Carolina Storage Wichita Falls | CSE Storage, LLC | 202 | 2027-05-01 | 2028-05-01 | Wichita | WEST | SS Started, FIS Started, No IA
Carolina Storage Young County | CSE STORAGE, LLC | 104.4 | 2027-05-01 | 2028-05-01 | Young | WEST | SS Started, FIS Started, No IA
Kinney County Energy | Kinney County Energy, LLC | 101.2 | 2027-05-01 | 2028-05-01 | Kinney | SOUTH | SS Completed, FIS Started, No IA
HarryoungBESS | Gransolar Texas Four LLC | 190.01 | 2027-05-01 | 2028-05-01 | Cameron | COASTAL | SS Completed, FIS Started, No IA
TRAVIS KIMBRO BESS | Travis Kimbro BESS LLC | 36.84 | 2027-05-01 | 2028-05-01 | Travis | SOUTH | SS Completed, FIS Started, No IA
BERRY BOOST BESS | GRIDSTOR, LLC | 203.2 | 2027-05-01 | 2028-05-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
THUNDER ROAD ENERGY STORAGE | Hecate Grid Thunder Road Storage LLC | 153.4 | 2027-05-01 | 2028-05-01 | Dallas | NORTH | SS Completed, FIS Started, No IA
Carpenter Energy Storage | GridStor LLC | 203.2 | 2027-05-01 | 2028-05-01 | Harris | HOUSTON | SS Started, FIS Started, No IA
Knickerbocker Storage SLF | Knickerbocker Solar LLC | 0 | 2027-06-01 | 2028-06-01 | Tom Green | WEST | SS Completed, FIS Started, No IA
Rockefeller Storage SLF | Mittel Rockefeller Solar LLC | 0 | 2027-06-01 | 2028-06-01 | Schleicher | WEST | SS Completed, FIS Started, No IA
Cumulus Grid BESS | Cumulus Grid, LLC | 210.74 | 2027-06-01 | 2028-06-01 | Ellis | NORTH | SS Completed, FIS Started, No IA
Holly Branch Storage | Holly Branch Solar, LLC | 115.32 | 2027-06-01 | 2028-06-01 | Robertson | NORTH | SS Completed, FIS Started, No IA
Pinnacle Point Energy Storage | GCI Pinnacle Point, LLC | 101.3 | 2027-06-01 | 2028-06-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Orbit Energy Storage | GCI Orbit Energy Storage, LLC | 501.94 | 2027-06-01 | 2028-06-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
Spinner Energy Storage | GCI Wolf Energy Storage, LLC | 125.63 | 2027-06-01 | 2028-06-01 | Bee | SOUTH | SS Completed, FIS Started, No IA
Paloma Energy Center BESS | Harrison Street Development, LLC | 53.6 | 2027-06-01 | 2028-06-01 | Colorado | SOUTH | SS Started, FIS Started, No IA
Easy Battery Energy Storage Center | Easy Wind Energy Center, LLC | 200 | 2027-06-01 | 2028-06-01 | Schleicher | WEST | SS Started, FIS Started, No IA
Canvasback BESS | Black Mountain Energy Storage II | 150.5 | 2027-06-01 | 2028-06-01 | Calhoun | COASTAL | SS Completed, FIS Started, No IA
RedSun BESS | Gransolar Texas Twenty Two | 84.04 | 2027-06-01 | 2028-06-01 | Burnet | SOUTH | SS Completed, FIS Started, No IA
Pleiades Storage | Pleiades Storage, LLC | 205.5 | 2027-06-01 | 2028-06-01 | Glasscock | WEST | SS Started, FIS Started, No IA
Port Bay ESC | FRESH AIR ENERGY II, LLC | 200 | 2027-06-01 | 2028-06-01 | Aransas | COASTAL | SS Completed, FIS Started, No IA
Paluxy Storage | S&S Renewables LLC | 511.68 | 2027-06-01 | 2028-06-01 | Victoria | SOUTH | SS Completed, FIS Started, No IA
Trenno BESS | JSB1, LLC | 204.16 | 2027-06-01 | 2028-06-01 | Johnson | NORTH | SS Completed, FIS Started, No IA
Grandfalls Storage | King Mountain Storage LLC | 205.9 | 2027-07-01 | 2028-07-01 | Upton | WEST | SS Completed, FIS Started, No IA
Inertia BESS 2 | Inertia Energy Storage, LLC | 100.77 | 2027-07-01 | 2028-07-01 | Haskell | WEST | SS Completed, FIS Started, IA
PEREGRINE BESS | CED Development Inc. | 150 | 2027-07-01 | 2028-07-01 | Goliad | SOUTH | SS Completed, FIS Started, No IA
Tidwell Prairie IV Energy Storage | Tidwell Prairie LLC | 200 | 2027-07-01 | 2028-07-01 | Robertson | NORTH | SS Completed, FIS Started, No IA
Keys Hollow Storage Phase II SLF | Keys Hollow Solar, LLC | 0 | 2027-07-01 | 2028-07-01 | Goliad | SOUTH | SS Completed, FIS Started, No IA
KEYS HOLLOW STORAGE SLF | Keys Hollow Solar, LLC | 0 | 2027-07-01 | 2028-07-01 | Goliad | SOUTH | SS Completed, FIS Started, No IA
Two Forks BESS | Two Forks LLC | 309 | 2027-07-01 | 2028-07-01 | Cooke | NORTH | SS Completed, FIS Started, No IA
Peregrine BESS 2 | CED Development Inc. | 150 | 2027-07-01 | 2028-07-01 | Goliad | SOUTH | SS Completed, FIS Started, No IA
Ayass BESS | Harvick BESS, LLC | 51.28 | 2027-07-01 | 2028-07-01 | Throckmorton | WEST | SS Completed, FIS Started, No IA
La Salle ESS | OCI La Salle ESS LLC | 503.9 | 2027-07-01 | 2028-07-01 | La Salle | SOUTH | SS Completed, FIS Started, No IA
Lazy U ESS 1 | Lazy U ESS 1 | 251.5 | 2027-07-01 | 2028-07-01 | Hardeman | WEST | SS Completed, FIS Started, No IA
Lazy U ESS 2 | Lazy U ESS 2 | 251.5 | 2027-07-01 | 2028-07-01 | Hardeman | WEST | SS Completed, FIS Started, No IA
SunShiner ESS | SunShiner ESS LLC | 200 | 2027-07-01 | 2028-07-01 | Zavala | SOUTH | SS Completed, FIS Started, No IA
Burgundy BESS | Burgundy BESS, LLC | 102.48 | 2027-07-01 | 2028-07-01 | Limestone | NORTH | SS Completed, FIS Started, No IA
Alamo City BESS | Alamo City BESS | 100 | 2027-07-01 | 2028-07-01 | Bexar | SOUTH | SS Started, FIS Started, No IA
RUSH ESS | OCI Solar Power LLC | 202.7 | 2027-07-01 | 2028-07-01 | Bexar | SOUTH | SS Completed, FIS Started, No IA
Prost ESS | Prost ESS LLC | 202.7 | 2027-07-01 | 2028-07-01 | Austin | SOUTH | SS Started, FIS Started, No IA
Tex-Bar ESS | Tex-Bar ESS LLC | 201.5 | 2027-07-01 | 2028-07-01 | Madison | NORTH | SS Started, FIS Started, No IA
PowerVault BESS | SMT Elm Mott BESS | 254.8 | 2027-07-01 | 2028-07-01 | McLennan | NORTH | SS Started, FIS Started, No IA
Kit Fox Storage | Kit Fox Storage, LLC | 153.6 | 2027-07-01 | 2028-07-01 | Henderson | NORTH | SS Completed, FIS Started, No IA
Millsing BESS | Millsing BESS | 501.6 | 2027-07-01 | 2028-07-01 | Grimes | NORTH | SS Started, FIS Started, No IA
Leopard BESS | Bobcat Energy Center, LLC | 264.24 | 2027-07-01 | 2028-07-01 | Victoria | SOUTH | SS Started, FIS Started, No IA
Sultan BESS | Sultan BESS | 203.8 | 2027-07-01 | 2028-07-01 | Bosque | NORTH | SS Completed, FIS Started, No IA
Barbers Hill BESS | Black Mountain Energy Storage II | 307.72 | 2027-07-01 | 2028-07-01 | Chambers | HOUSTON | SS Completed, FIS Completed, No IA
Sunscape Renewable Energy Storage SLF | Sunscape Renewable Energy LLC | 0 | 2027-07-01 | 2028-07-01 | Nueces | COASTAL | SS Completed, FIS Started, No IA
Pecan BESS | Gransolar Texas Three LLC | 157.12 | 2027-07-01 | 2028-07-01 | Leon | NORTH | SS Completed, FIS Started, No IA
Steelhead Energy Storage | GRS BESS TEXAS SEVEN, LLC | 193.66 | 2027-07-01 | 2028-07-01 | Fannin | NORTH | SS Completed, FIS Started, No IA
Ross Storage | S&S Renewables, LLC | 510.99 | 2027-07-01 | 2028-07-01 | Refugio | COASTAL | SS Completed, FIS Started, No IA
Felix Storage | Felix 1, LLC | 100.54 | 2027-07-01 | 2028-07-01 | Wilbarger | WEST | SS Completed, FIS Started, No IA
TOCE TX BESS 2 | TOCE TX BESS 2, LLC | 506.1 | 2027-08-01 | 2028-08-01 | Wharton | SOUTH | SS Completed, FIS Started, No IA
High Chap Storage | HIGH CHAPARRAL SOLAR PROJECT LLC | 71.78 | 2027-08-01 | 2028-08-01 | Brazoria | COASTAL | SS Completed, FIS Started, No IA
Marcos BESS | GRS BESS Texas Eight LLC | 115.88 | 2027-08-01 | 2028-08-01 | Victoria | SOUTH | SS Completed, FIS Started, No IA
Benitoite Storage | BT Van Storage, LLC | 125.65 | 2027-08-01 | 2028-08-01 | Van Zandt | NORTH | SS Started, FIS Started, No IA
Anawa La BESS | EIA Properties, Ltd. | 103.7 | 2027-08-01 | 2028-08-01 | Hidalgo | SOUTH | SS Started, FIS Started, No IA
El Molino Storage SLF | El Molino Solar, LLC | 0 | 2027-09-01 | 2028-09-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
SCOTT CROSSING STORAGE SLF | FRESH AIR ENERGY II, LLC | 0 | 2027-09-01 | 2028-09-01 | Haskell | WEST | SS Completed, FIS Started, No IA
UNICORN BESS | Unicorn Energies | 278.98 | 2027-09-01 | 2028-09-01 | Fort Bend | HOUSTON | SS Completed, FIS Started, No IA
PALO VERDE BESS | RWE Clean Energy Development, LLC | 150 | 2027-09-01 | 2028-09-01 | San Patricio | COASTAL | SS Started, FIS Started, No IA
Jumping Cactus Storage | Dove Run Solar Project, LLC | 125.37 | 2027-09-01 | 2028-09-01 | Duval | SOUTH | SS Completed, FIS Started, No IA
Dove Wing Storage | Dove Run Solar Project, LLC | 122.41 | 2027-09-01 | 2028-09-01 | Duval | SOUTH | SS Completed, FIS Started, No IA
Cottontail Energy Center | Mission Clean Energy LLC | 200.85 | 2027-10-01 | 2028-10-01 | Colorado | SOUTH | SS Completed, FIS Started, No IA
Camino Ranch Storage SLF | Camino Solar Ranch, LLC | 298.06 | 2027-10-01 | 2028-10-01 | Houston | NORTH | SS Completed, FIS Started, No IA
Camino Ranch Storage 2 SLF | Camino Ranch Solar LLC | 238.45 | 2027-10-01 | 2028-10-01 | Houston | NORTH | SS Completed, FIS Started, No IA
Chacon Creek | Cattlemen BESS LLC | 181.9 | 2027-10-01 | 2028-10-01 | Medina | SOUTH | SS Started, FIS Started, No IA
Wander Waters BESS | Wander Waters BESS LLC | 303.5 | 2027-10-01 | 2028-10-01 | Wilbarger | WEST | SS Started, FIS Started, No IA
Oak Tree Energy Storage | Live Oak Energy Storage, LLC | 310.2 | 2027-11-01 | 2028-11-01 | Lavaca | SOUTH | SS Completed, FIS Started, No IA
Horse Wrangler Storage | Horse Wrangler Solar Project, LLC | 102.07 | 2027-12-01 | 2028-12-01 | Karnes | SOUTH | SS Completed, FIS Started, No IA
Texas Sage Storage | Texas Sage Solar Project, LLC | 51.7 | 2027-12-01 | 2028-12-01 | Wilson | SOUTH | SS Started, FIS Started, No IA
Becerra Creek Storage 2 | Bordas Renewable Energy, LLC | 125.62 | 2027-12-01 | 2028-12-01 | Webb | SOUTH | SS Completed, FIS Started, No IA
Panhandle Flagship Storage | Panhandle Solar Group Operating Company LLC | 371.7 | 2027-12-01 | 2028-12-01 | Carson | PANHANDLE | SS Completed, FIS Started, No IA
Short Creek BESS | Wichita Solar I, LLC | 150.51 | 2027-12-01 | 2028-12-01 | Wichita | WEST | SS Completed, FIS Started, No IA
Live Oak Bayou Storage SLF | FRESH AIR ENERGY II, LLC | 0 | 2027-12-01 | 2028-12-01 | Matagorda | COASTAL | SS Completed, FIS Started, No IA
Outer Loop BESS | Black Mountain Energy Storage II | 201.2 | 2027-12-01 | 2028-12-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Augite Storage | BT Augite Storage, LLC | 151.41 | 2027-12-01 | 2028-12-01 | Starr | SOUTH | SS Started, FIS Started, No IA
Cannon Storage SLF | Cannon Solar, LLC | 0 | 2027-12-01 | 2028-12-01 | Gonzales | SOUTH | SS Completed, FIS Started, No IA
Bar Candela Storage SLF | Bar Candela Storage Project LLC | 0 | 2027-12-01 | 2028-12-01 | Freestone | NORTH | SS Completed, FIS Completed, No IA
Ash Creek BESS | ACTX BESS Project LLC | 309 | 2027-12-01 | 2028-12-01 | Hill | NORTH | SS Completed, FIS Started, No IA
Great Rock BESS | Black Mountain Energy Storage II | 300.9 | 2027-12-01 | 2028-12-01 | Leon | NORTH | SS Completed, FIS Started, No IA
Proteus London-Leigh Storage SLF | London Leigh Solar, LLC | 0 | 2027-12-01 | 2028-12-01 | Glasscock | WEST | SS Completed, FIS Started, No IA
Beitel Energy Storage | Brazos Energy Storage, LLC | 200.6 | 2027-12-01 | 2028-12-01 | Jack | NORTH | SS Completed, FIS Started, No IA
Vaughn Energy Storage | Vaughn Battery Storage, LLC | 200.6 | 2027-12-01 | 2028-12-01 | Grimes | NORTH | SS Completed, FIS Started, No IA
Cedar Draw BESS | Cedar Draw Solar LLC | 225.7 | 2027-12-01 | 2028-12-01 | Scurry | WEST | SS Started, FIS Started, No IA
Sunrose Renewable Energy Storage SLF | Sunrose Renewable Energy LLC | 300.88 | 2027-12-01 | 2028-12-01 | Austin | SOUTH | SS Started, FIS Started, No IA
Findley BESS | Gransolar Texas Sixteen, LLC | 51.74 | 2028-01-01 | 2029-01-01 | Limestone | NORTH | SS Completed, FIS Started, No IA
Rosebud Storage | Rosebud Storage, LLC | 89.1 | 2028-01-01 | 2029-01-01 | Falls | NORTH | SS Completed, FIS Started, No IA
Tiger Storage | Vaca Del Sol, LLC | 251.04 | 2028-03-01 | 2029-03-01 | Jones | WEST | SS Completed, FIS Started, No IA
French Riviera Storage | Arana Creek Battery Storage LLC | 75 | 2028-05-01 | 2029-05-01 | Kleberg | COASTAL | SS Completed, FIS Started, No IA
Val Vista Grid BESS | Val Vista Grid, LLC | 209.32 | 2028-06-01 | 2029-06-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Snap Jaw BESS | Moccasin Pointe Grid, LLC | 201.28 | 2028-06-01 | 2029-06-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA
Stump Tail BESS | Moccasin Pointe Grid, LLC | 301.69 | 2028-06-01 | 2029-06-01 | Harris | HOUSTON | SS Completed, FIS Completed, No IA
Seguro Grid | Val Vista Grid, LLC | 201.33 | 2028-06-01 | 2029-06-01 | Hidalgo | SOUTH | SS Completed, FIS Started, No IA
Diamond Cowboy Storage | Diamond B Storage, LLC | 103.5 | 2028-06-01 | 2029-06-01 | San Patricio | COASTAL | SS Started, FIS Started, No IA
Cantaloupe Storage | Saragosa Del Sol Energy, LLC | 251.05 | 2028-07-01 | 2029-07-01 | Reeves | WEST | SS Completed, FIS Started, IA
Moonlit Bayou Storage | Moonlit Bayou Energy Center, LLC | 209.23 | 2028-07-01 | 2029-07-01 | Fayette | SOUTH | SS Started, FIS Started, No IA
Masava Storage | Savannah Oaks Solar Project, LLC | 261.51 | 2028-09-01 | 2029-09-01 | Madison | NORTH | SS Completed, FIS Started, No IA
Strawberry Acres Storage | Strawberry Acres Energy Center, LLC | 156.73 | 2028-09-01 | 2029-09-01 | Wilson | SOUTH | SS Completed, FIS Started, No IA
Buffalo Prairie Storage | Buffalo Meadow Energy Center, LLC | 313.51 | 2028-09-01 | 2029-09-01 | Robertson | NORTH | SS Completed, FIS Started, No IA
Diablo Campo Storage | Diablo Campo Energy Center, LLC | 313.54 | 2028-09-01 | 2029-09-01 | Goliad | SOUTH | SS Completed, FIS Started, No IA
Coyote Den Storage | Coyote Den Energy Center, LLC | 156.61 | 2028-09-01 | 2029-09-01 | Karnes | SOUTH | SS Completed, FIS Started, No IA
ARTIO ENERGY STORAGE | Artio Energy Storage LLC | 205.94 | 2028-10-01 | 2029-10-01 | Collin | NORTH | SS Completed, FIS Started, No IA
Oriole BES | Rolling Plains Solar | 150.39 | 2028-12-01 | 2029-12-01 | Knox | WEST | SS Completed, FIS Started, No IA
Limewood Storage | Limewood Bell Renewables LLC | 50 | 2028-12-01 | 2029-12-01 | Bell | NORTH | SS Completed, FIS Started, IA
Zeissel Storage SLF | ZSS Power, LLC | 0 | 2028-12-01 | 2029-12-01 | Knox | WEST | SS Completed, FIS Started, IA
Big Rooter East Storage SLF | Big Rooter East, LLC | 0 | 2029-01-01 | 2030-01-01 | Robertson | NORTH | SS Started, FIS Started, No IA
Papley Storage | Papley Storage, LLC | 201.07 | 2029-07-01 | 2030-07-01 | Maverick | SOUTH | SS Completed, FIS Started, No IA
Diamondback BESS | Diamondback BESS | 203.8 | 2030-06-01 | 2031-06-01 | Starr | SOUTH | SS Completed, FIS Started, No IA
Woodland Energy Storage | Woodland Energy Storage, LLC | 207.6 | 2030-10-01 | 2031-10-01 | Bosque | NORTH | SS Completed, FIS Started, No IA
Hyacinth Storage | Hyacinth Storage, LLC | 103.05 | 2030-12-01 | 2031-12-01 | Harris | HOUSTON | SS Completed, FIS Started, No IA

## Existing Assets
Modo Energy Battery Pipeline - May 2024 - December 2030
Site Name | Owner | Power (MW) | Energy (MWh) | Duration (hrs) | Commissioning Date | Load Zone | County | Latitude | Longitude | Co-Located | QSE | DME
Notrees | Duke Energy | 36 | 13.6 | 0.37778 | 2013-01-01 | West | Winkler | 31.995 | -102.8283 | TRUE | DUKE ENERGY RENEWABLE SERVICES LLC (QSE) | NOTREES WINDPOWER LP
OCI Alamo | Oci Solar Power | 1 | 0.25 | 0.25 | 2016-08-01 | South | Bexar |  |  | FALSE | CPS ENERGY WIND | OCI ALAMO 1 LLC
Kingsbery | Austin Energy | 1.5 | 3 | 2 | 2017-01-01 | South | Travis | 30.266 | -97.6861 | TRUE | Austin Energy | Austin Energy
Blue Summit | NextEra Energy Resources | 30 | 12.6 | 0.42 | 2017-02-01 | West | Wilbarger | 34.299 | -99.399 | FALSE | NEXTERA ENERGY MARKETING LLC (SQ12) | BLUE SUMMIT STORAGE LLC
Tos (DGR) | Other | 2 | 2 | 1 | 2017-10-01 | West | Midland |  |  | FALSE | NRG TEXAS POWER LLC | NRG TEXAS POWER LLC
Inadale | RWE | 9.9 | 9.9 | 1 | 2018-01-01 | West | Nolan | 32.4969 | -100.5797 | FALSE | RWE CLEAN ENERGY QSE LLC (QSE) | RWE CLEAN ENERGY LLC
Pyron | RWE | 9.9 | 9.9 | 1 | 2018-01-01 | West | Fisher | 32.5886 | -100.6728 | TRUE | RWE CLEAN ENERGY QSE LLC (QSE) | RWE CLEAN ENERGY LLC
Prospect (DGR) | Quinbrook | 9.9 | 9.9 | 1 | 2020-01-01 | South | BRAZORIA | 29.1492 | -95.6511 | FALSE | None,UNIPER GLOBAL COMMODITIES NORTH AMERICA LLC (SQ3),HABITAT ENERGY INC (QSE) | WEST COLUMBIA STORAGE LLC,BYRD RANCH STORAGE LLC
Port Lavaca (DGR) | Key Capture Energy | 9.9 | 11.9 | 1.202 | 2020-02-01 | Houston | Calhoun | 28.5867 | -96.6838 | FALSE | SOUTH TEXAS ELECTRIC CO OP INC (SQ3) | KEY CAPTURE ENERGY LLC 2
Rabbit Hill | Ormat | 9.9 | 9.9 | 1 | 2020-03-01 | South | Williamson | 30.5878 | -97.687 | FALSE | VIRIDITY ENERGY SOLUTIONS INC (QSE),BOSTON ENERGY TRADING AND MARKETING LLC (SQ9) | VIRIDITY ENERGY SOLUTIONS INC
Worsham (DGR) | Key Capture Energy | 9.9 | 17.9 | 1.8081 | 2020-04-01 | West | Reeves | 31.3566 | -103.3365 | FALSE | MP2 ENERGY LLC,SHELL ENERGY NORTH AMERICA (US) LP (SQ2) | KEY CAPTURE ENERGY LLC
Flat Top (DGR) | Key Capture Energy | 9.9 | 16.5 | 1.6667 | 2020-05-01 | West | Reeves | 31.1973 | -103.3618 | FALSE | MP2 ENERGY LLC,SHELL ENERGY NORTH AMERICA (US) LP (SQ2) | KEY CAPTURE ENERGY LLC
Odessa SW (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 9.9 | 1 | 2020-08-01 | West | Ector | 31.8713 | -102.3984 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Alvin (DGR) | Broad Reach Power LLC,ENGIE | 10 | 10 | 1 | 2020-09-01 | Houston | Brazoria | 29.4332 | -95.2494 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Commerce St (DGR) | CPS Energy | 10 | 10 | 1 | 2020-10-01 | South | Bexar | 29.4344 | -98.6176 | TRUE | CPS ENERGY (QSE) | CPS ENERGY
Johnson City | Other | 2.3 | 2.3 | 1 | 2020-11-01 | South | Blanco |  |  | FALSE | LOWER COLORADO RIVER AUTHORITY | PEDERNALES ELECTRIC COOPERATIVE INC
Brazoria (DGR) | Broad Reach Power LLC,ENGIE | 10 | 10 | 1 | 2020-11-01 | Houston | Brazoria | 29.0626 | -95.5776 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Heights (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 9.9 | 1 | 2020-12-01 | Houston | Galveston | 29.3896 | -94.9499 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Angelton (DGR) | Broad Reach Power LLC,ENGIE | 10 | 10 | 1 | 2020-12-01 | Houston | Brazoria | 29.1671 | -95.4407 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Magnolia (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 9.9 | 1 | 2021-01-01 | Houston | Galveston | 29.4883 | -95.1339 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Sweeny (DGR) | Broad Reach Power LLC,ENGIE | 10 | 10 | 1 | 2021-05-01 | Houston | Brazoria | 29.0556 | -95.6872 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Hoefs Road (DGR) | Hunt Energy Network | 2 | 2 | 1 | 2021-05-01 | West | Reeves | 31.0312 | -103.4626 | FALSE | HEN POWER MARKETING LLC (QSE) | HEN INFRASTRUCTURE LLC
Flower Valley 1 (DGR) | Jupiter Power | 9.9 | 19.8 | 2 | 2021-05-01 | West | Reeves | 31.1973 | -103.3618 | FALSE | TENASKA POWER SERVICES CO (QSE),TENASKA POWER SERVICES CO | FLOWER VALLEY LLC
Gambit | Tesla,Plus Power | 100 | 200 | 2 | 2021-05-01 | Houston | Brazoria | 29.168 | -95.4451 | FALSE | ENGIE ENERGY MARKETING NA INC (SQ23) | TESLA,GAMBIT ENERGY STORAGE LLC
Dickinson (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 9.9 | 1 | 2021-06-01 | Houston | Galveston | 29.4613 | -95.057 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Swoose (DGR) | Jupiter Power | 9.9 | 19.8 | 2 | 2021-07-01 | West | Ward | 31.4511 | -103.0962 | FALSE | TENASKA POWER SERVICES CO (QSE),TENASKA POWER SERVICES CO | SWOOSE LLC
Triple Butte (DGR) | Jupiter Power | 7.5 | 15 | 2 | 2021-07-01 | West | Pecos | 30.7596 | -103.0679 | FALSE | TENASKA POWER SERVICES CO (QSE),TENASKA POWER SERVICES CO | TRIPLE BUTTE LLC
Deep Greek (DGR) | SER Capital Partners,Gore Street Capital | 10 | 20 | 2 | 2021-09-01 | West | Scurry |  |  | FALSE | None,TENASKA POWER SERVICES CO | SNYDER ESS ASSETS LLC
Toyah Power Station (DGR) | Hunt Energy Network | 10.4 | 9.9 | 0.95192 | 2021-09-01 | West | REEVES | 31.1139 | -103.6655 | FALSE | HEN POWER MARKETING LLC (QSE),HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC,HEN INFRASTRUCTURE LLC 2
Loop 463 (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 10 | 1.0101 | 2021-09-01 | South | Victoria | 28.8165 | -97.0749 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Westover (DGR) | Other,Gore Street Capital | 9.9 | 9.9 | 1 | 2021-09-01 | West | Ector |  |  | FALSE | None,TENASKA POWER SERVICES CO | WESTOVER ESS ASSETS LLC
Sweetwater (DGR) | SER Capital Partners,Gore Street Capital | 10 | 20 | 2 | 2021-09-01 | West | Nolan |  |  | FALSE | None,TENASKA POWER SERVICES CO | SWEETWATER ESS ASSETS LLC
Eunice | Orsted | 40.3 | 40 | 0.99256 | 2021-09-01 | West | Andrews | 32.1164 | -102.5283 | TRUE | TENASKA POWER SERVICES CO (QSE) | 2W PERMIAN SOLAR LLC
Chisholm | Astral Electricity LLC | 100 | 125 | 1.25 | 2021-10-01 | North | Tarrant | 32.9044 | -97.3861 | FALSE | TENASKA POWER SERVICES CO (QSE),TENASKA POWER SERVICES CO | CHISHOLM GRID LLC
Bat Cave | Broad Reach Power LLC,ENGIE | 100.5 | 110 | 1.0945 | 2021-10-01 | South | Mason | 30.7377 | -99.2318 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Ranchtown (DGR) | Broad Reach Power LLC,ENGIE | 10 | 9.9 | 0.99 | 2021-10-01 | South | Bexar | 29.6179 | -98.736 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
North Fork | Broad Reach Power LLC,ENGIE | 100 | 110 | 1.1 | 2021-10-01 | South | Williamson | 30.749 | -97.8757 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Lily | Enel Green Power | 50 | 76 | 1.52 | 2021-11-01 | North | Kaufman | 32.5333 | -96.429 | TRUE | ENEL TRADING NORTH AMERICA LLC (SQ5) | ENEL TRADING NORTH AMERICA LLC
Decordova 3 | Vistra corp | 64.2 | 64.2 | 1 | 2022-01-01 | North | Hood | 32.4031 | -97.7006 | FALSE | LUMINANT ENERGY COMPANY LLC (QSE) | DECORDOVA BESS LLC
Zapata 2 (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 10 | 1.0101 | 2022-02-01 | South | Zapata | 26.9327 | -99.2337 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Pueblo 1 (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 10 | 1.0101 | 2022-02-01 | South | Maverick | 28.6789 | -100.4637 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Zapata 1 (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 10 | 1.0101 | 2022-02-01 | South | Zapata | 26.9327 | -99.2337 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Lopeno (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 10 | 1.0101 | 2022-03-01 | South | Zapata | 26.6876 | -99.1094 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Pueblo 2 (DGR) | Broad Reach Power LLC,ENGIE | 9.9 | 10 | 1.0101 | 2022-03-01 | South | Maverick | 28.6789 | -100.4637 | FALSE | BROAD REACH POWER LLC (QSE),BROAD REACH QSE I LLC ( | BRP INTERMEDIATECO I LLC,BRP INTERMEDIATECO I LLC
Flower Valley 2 | Jupiter Power | 101 | 200 | 1.9802 | 2022-04-01 | West | Reeves | 31.1973 | -103.3618 | FALSE | TENASKA POWER SERVICES CO | FLOWER VALLEY II LLC
Crossett Power 2 | Jupiter Power | 101.5 | 101.5 | 1 | 2022-05-01 | West | Crane | 31.1917 | -102.3172 | FALSE | TENASKA POWER SERVICES CO | CROSSETT POWER MANAGEMENT LLC
Lonestar | Hunt Energy Network | 9.95 | 9.9 | 0.99497 | 2022-05-01 | West | Ward | 31.5949 | -103.2498 | FALSE | HEN POWER MARKETING LLC (QSE),HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC
Republic Road | Key Capture Energy | 50 | 50 | 1 | 2022-05-01 | North | Robertson | 30.8814 | -96.6254 | FALSE | SHELL ENERGY NORTH AMERICA (US) LP (SQ2) | KEY CAPTURE ENERGY LLC
Saddleback (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2022-05-01 | West | Reeves | 31.3329 | -103.4984 | FALSE | HEN POWER MARKETING LLC,HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC,HEN INFRASTRUCTURE LLC 2
Faulkner (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2022-05-01 | West | Reeves | 31.2624 | -103.7949 | FALSE | HEN POWER MARKETING LLC (QSE),HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC,HEN INFRASTRUCTURE LLC 2
Crossett Power 1 | Jupiter Power | 101.5 | 101.5 | 1 | 2022-05-01 | West | Crane | 31.1917 | -102.3172 | FALSE | TENASKA POWER SERVICES CO,ZEPHYR ASSET MANAGEMENT LLC (QSE) | CROSSETT POWER MANAGEMENT LLC,CROSSETT POWER MANAGEMENT LLC 1
Cedarvale (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2022-06-01 | West | Reeves | 31.5141 | -103.4524 | FALSE | HEN POWER MARKETING LLC (QSE),HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC
Azure Sky Solar | Enel Green Power | 77 | 77.6 | 1.0078 | 2022-06-01 | West | Haskell | 32.9989 | -99.5985 | TRUE | ENEL TRADING NORTH AMERICA LLC (SQ6) | ENEL TRADING NORTH AMERICA LLC
Coyote Springs | Hunt Energy Network | 9.9 | 9.9 | 1 | 2022-06-01 | West | Reeves | 31.3947 | -103.6303 | FALSE | HEN POWER MARKETING LLC (QSE),HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC
Rattlesnake (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2022-06-01 | West | Ward | 31.569 | -103.2266 | FALSE | HEN POWER MARKETING LLC,HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC
Saragosa (DGR) | Other | 9.9 | 9.9 | 1 | 2022-07-01 | West | Reeves |  |  | FALSE | MP2 ENERGY LLC | MATTA POWER STATION LLC
Swoose 2 | Jupiter Power | 101 | 200 | 1.9802 | 2022-08-01 | West | Ward | 31.4511 | -103.3618 | FALSE | TENASKA POWER SERVICES CO | SWOOSE II LLC
Catarina (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2022-08-01 | South | Dimmit | 28.347 | -99.6737 | FALSE | HEN POWER MARKETING LLC (QSE),HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC
Decordova 4 | Vistra corp | 64.2 | 64.2 | 1 | 2022-09-01 | North | Hood | 32.4031 | -97.7006 | FALSE | LUMINANT ENERGY COMPANY LLC (QSE) | DECORDOVA BESS LLC
Decordova 2 | Vistra corp | 67.3 | 67.3 | 1 | 2022-09-01 | North | Hood | 32.4031 | -97.7006 | FALSE | LUMINANT ENERGY COMPANY LLC (QSE) | DECORDOVA BESS LLC
Decordova 1 | Vistra corp | 67.3 | 67.3 | 1 | 2022-09-01 | North | Hood | 32.4031 | -97.7006 | FALSE | LUMINANT ENERGY COMPANY LLC (QSE) | DECORDOVA BESS LLC
Noble 2 | National Grid Renewables | 62.5 | 62.5 | 1 | 2022-10-01 | North | Denton | 33.2615 | -97.2381 | TRUE | NG RENEWABLES ENERGY SERVICES LLC (QSE) | BT NOBLE SOLAR LLC
Noble 1 | National Grid Renewables | 62.5 | 62.5 | 1 | 2022-10-01 | North | Denton | 33.2615 | -97.2381 | TRUE | NG RENEWABLES ENERGY SERVICES LLC (QSE) | BT NOBLE SOLAR LLC
Bryd Ranch | GlidePath | 50 | 50 | 1 | 2022-11-01 | Houston | Brazoria | 29.056 | -95.686 | FALSE | UNIPER GLOBAL COMMODITIES NORTH AMERICA LLC (SQ4),HABITAT ENERGY INC (QSE) | BYRD RANCH STORAGE LLC
North Columbia | Key Capture Energy | 50 | 50 | 1 | 2022-12-01 | Houston | Brazoria | 29.1592 | -95.6626 | FALSE | SHELL ENERGY NORTH AMERICA (US) LP (SQ2) | KEY CAPTURE ENERGY LLC
Endurance Park | Key Capture Energy | 50 | 50 | 1 | 2023-01-01 | West | Scurry | 32.8558 | -100.9917 | FALSE | SHELL ENERGY NORTH AMERICA (US) LP (SQ2) | KEY CAPTURE ENERGY LLC
Holcomb (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2023-01-01 | South | La Salle | 28.0353 | -99.3617 | FALSE | HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC
Screwbean (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2023-02-01 | West | Culberson | 31.8214 | -104.0451 | FALSE | HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC
Madero Grid 2 | Eolian | 100 | 100 | 1 | 2023-04-01 | South | Hidalgo | 26.1669 | -98.325 | FALSE | ENGIE ENERGY MARKETING NA INC | MADERO GRID LLC
Madero Grid 1 | Eolian | 100 | 100 | 1 | 2023-04-01 | South | Hidalgo | 26.1698 | -98.3298 | FALSE | MADERO GRID LLC | MADERO GRID LLC
Silicon Hill 2 | Key Capture Energy | 50 | 50 | 1 | 2023-05-01 | South | Travis | 30.4122 | -97.574 | FALSE | SHELL ENERGY NORTH AMERICA (US) LP | KEY CAPTURE ENERGY LLC
Silicon Hill 1 | Key Capture Energy | 50 | 50 | 1 | 2023-05-01 | South | TRAVIS | 30.4122 | -97.574 | FALSE | SHELL ENERGY NORTH AMERICA (US) LP | KEY CAPTURE ENERGY LLC
Gomez (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2023-05-01 | West | PECOS |  |  | FALSE | HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC 1
Olney | Hunt Energy Network | 9.9 | 9.9 | 1 | 2023-05-01 | West | Young |  |  | FALSE | HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC 1
SP TX-12B | Ormat | 22.7 | 22.7 | 1 | 2023-06-01 | West | Upton |  |  | TRUE | BOSTON ENERGY TRADING AND MARKETING LLC | VESI UPTON COUNTY BESS LLC
Blue Jay | Enel Green Power | 59 | 89 | 1.5085 | 2023-07-01 | North | Grimes | 30.7115 | -96.0641 | TRUE | ENEL TRADING NORTH AMERICA LLC | ENEL TRADING NORTH AMERICA LLC
Pyron 2B | RWE | 15 | 15 | 1 | 2023-07-01 | West | Fisher | 32.5886 | -100.6728 | TRUE | RWE CLEAN ENERGY QSE LLC (QSE) | RWE CLEAN ENERGY LLC
Pyron 2A | RWE | 15 | 15 | 1 | 2023-07-01 | West | Fisher | 32.5886 | -100.6728 | TRUE | RWE CLEAN ENERGY QSE LLC (QSE) | RWE CLEAN ENERGY LLC
Wolf Tank | Aypa Power | 150 | 150 | 1 | 2023-07-01 | South | Webb | 27.5772 | -99.276 | FALSE | ENEL TRADING NORTH AMERICA LLC | BOSTON ENERGY TRADING AND MARKETING LLC
Roseland | Enel Green Power | 50 | 50 | 1 | 2023-07-01 | North | Falls | 31.4596 | -96.8244 | TRUE | ENEL TRADING NORTH AMERICA LLC | ENEL TRADING NORTH AMERICA LLC
High Lonesome | Enel Green Power | 50 | 50 | 1 | 2023-08-01 | West | Crockett | 31.1717 | -101.8811 | TRUE | ENEL TRADING NORTH AMERICA LLC | ENEL TRADING NORTH AMERICA LLC
River Valley 1 | Key Capture Energy | 50 | 50 | 1 | 2023-08-01 | South | Williamson | 30.4148 | -97.357 | FALSE | SHELL ENERGY NORTH AMERICA (US) LP | KEY CAPTURE ENERGY LLC
River Valley 2 | Key Capture Energy | 50 | 50 | 1 | 2023-08-01 | South | Williamson | 30.4143 | -97.3552 | FALSE | SHELL ENERGY NORTH AMERICA (US) LP | KEY CAPTURE ENERGY LLC
Roadrunner (Queen) | Enel Green Power | 50 | 50 | 1 | 2023-08-01 | West | Upton |  |  | TRUE | ENEL TRADING NORTH AMERICA LLC (SQ2) | ENEL TRADING NORTH AMERICA LLC
Cunningham | ACCIONA Energ√≠a | 190 | 380 | 2 | 2023-09-01 | North | Hunt | 33.0043 | -96.0759 | FALSE | BOSTON ENERGY TRADING AND MARKETING LLC | BT CUNNINGHAM STORAGE LLC
Junction (DGR) | Hunt Energy Network | 9.9 | 9.9 | 1 | 2023-10-01 | South | Kimble | 30.4925 | -99.7702 | FALSE | HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC 1
Bay City | SMT Energy | 9.9 | 9.9 | 1 | 2023-11-01 | Houston | Matagorda | 28.9876 | -95.9698 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
Azure Sky Wind | Enel Green Power | 121.8 | 180 | 1.4778 | 2023-11-01 | West | Throckmorton | 32.9989 | -99.5985 | TRUE | ENEL TRADING NORTH AMERICA LLC | ENEL TRADING NORTH AMERICA LLC
Ranchland Wind 1 | Enel Green Power | 35.2 | 35.2 | 1 | 2023-11-01 | West | Callahan |  |  | TRUE | ENEL TRADING NORTH AMERICA LLC | ENEL TRADING NORTH AMERICA LLC
Ranchland Wind 2 | Enel Green Power | 36.3 | 36.3 | 1 | 2023-11-01 | West | Callahan |  |  | TRUE | ENEL TRADING NORTH AMERICA LLC | ENEL TRADING NORTH AMERICA LLC
Myrtle Storage U2 | TotalEnergies | 74.3 | 119.56 | 1.6092 | 2023-11-01 | Houston | Brazoria | 29.2392 | -95.3964 | FALSE | TotalEnergies | TotalEnergies
Myrtle Storage U1 | TotalEnergies | 74.9 | 124.44 | 1.6614 | 2023-11-01 | Houston | Brazoria | 29.2392 | -95.3964 | TRUE | TotalEnergies | TotalEnergies
VAL VERDE BESS (DGR) | Hunt Energy Network | 10 | 10 | 1 | 2023-12-01 | South | Hidalgo | 29.7275 | -100.7943 | FALSE | HEN POWER MARKETING LLC (SQ1) | HEN INFRASTRUCTURE LLC 1
SMT Los Fresnos (DGR) | SMT Energy | 10 | 10 | 1 | 2023-12-01 | South | Cameron | 26.0747 | -97.5232 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
SMT Garceno Bess (DGR) | SMT Energy | 10 | 10 | 1 | 2023-12-01 | Houston | Matagorda | 28.9876 | -95.9698 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
North Mercedes BESS (DGR) | SMT Energy | 10 | 10 | 1 | 2023-12-01 | South | Hidalgo | 26.2305 | -97.9126 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
SMT SANTA ROSA (DGR) | SMT Energy | 10 | 10 | 1 | 2023-12-01 | South | Cameron | 26.2325 | -97.8232 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
SMT Elsa (DGR) | SMT Energy | 10 | 10 | 1 | 2023-12-01 | South | Hidalgo | 26.2961 | -98.0096 | TRUE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
SMT RIO GRANDE CITY BESS (DGR) | SMT Energy | 10 | 10 | 1 | 2023-12-01 | South | Starr | 26.4087 | -98.9374 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
Timberwolf Bess | Spearmint Energy | 150 | 300 | 2 | 2023-12-01 | West | Crane | 31.2335 | -102.3085 | FALSE | TENASKA POWER SERVICES CO,TENASKA POWER SERVICES CO | TIMBERWOLF BESS
Sun Valley Bess 2 | ENGIE | 47.3 | 46.7 | 0.98732 | 2023-12-01 | North | Hill | 31.8698 | -100.015 | TRUE | ENGIE ENERGY MARKETING NA INC (SQ38) | SUN VALLEY STORAGE LLC
Sun Valley Bess 1 | ENGIE | 54.1 | 53.3 | 0.98521 | 2024-01-01 | North | Hill | 31.8698 | -97.015 | TRUE | ENGIE ENERGY MARKETING NA INC (SQ38) | SUN VALLEY STORAGE LLC
Rodeo Ranch Energy Storage U1 | Plus Power | 150 | 300 | 2 | 2024-01-01 | West | Reeves | 31.2631 | -103.5712 | FALSE | ENGIE ENERGY MARKETING NA INC (SQ51) | GAMBIT ENERGY STORAGE LLC
Rodeo Ranch Energy Storage U2 | Plus Power | 150 | 300 | 2 | 2024-01-01 | West | Reeves | 31.2631 | -103.5712 | FALSE | ENGIE ENERGY MARKETING NA INC (SQ51) | GAMBIT ENERGY STORAGE LLC
North Alamo Bess | SMT Energy | 10 | 10 | 1 | 2024-01-01 | South | Hidalgo | 26.2307 | -98.114 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
Mayberry Bess | SMT Energy | 10 | 10 | 1 | 2024-01-01 | Houston | Cameron |  |  | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
SMT Harlingen II | SMT Energy | 10 | 10 | 1 | 2024-01-01 | Houston | Cameron | 26.18 | -97.7256 | FALSE | TENASKA POWER SERVICES CO | SMT TX MANAGEMENT LLC
House Mountain BESS | Jupiter Power | 63 | 126 | 2 | 2024-01-01 | West | Brewster | 30.4957 | -103.451 | FALSE | TENASKA POWER SERVICES CO | HOUSE MOUNTAIN LLC
Cameron Storage | Ingka Investments | 18 | 18 | 1 | 2024-03-01 | South | Cameron | 26.1953 | -97.4661 | TRUE
Diboll Bess | Hunt Energy Network | 9.95 | 9.95 | 1 | 2024-03-01 | North | Angelina | 31.1938 | -94.7982 | FALSE
St. Gall I Energy Storage | Jupiter Power | 102.6 | 200 | 1.9493 | 2024-03-01 | West | Pecos | 30.9244 | -102.9536 | FALSE
Mustang Creek Storage | Enel Green Power | 70.5 | 70.5 | 1 | 2024-03-01 | South | Jackson | 32.3067 | -99.1646 | TRUE
Zier Storage | Cypress Creek Renewables | 40.41 | 80 | 1.9797 | 2024-04-01 | South | Kinney | 29.351 | -100.562 | TRUE
LIBRA BESS | ENGIE | 206.21 | 206.21 | 1 | 2024-04-01 | South | Guadalupe | 26.6529 | -98.0149 | FALSE
Lufkin South BESS | Hunt Energy Network | 9.95 | 9.95 | 1 | 2024-02-01 | North | Angelina |  |  | FALSE
Hamilton BESS | Hunt Energy Network | 9.95 | 9.95 | 1 | 2024-02-01 | West | Val Verde | 29.806 | -100.8045 | FALSE
Judkins BESS | Hunt Energy Network | 9.95 | 9.95 | 1 | 2024-02-01 | West | Ector |  |  | FALSE
Garden City East BESS | Hunt Energy Network | 9.95 | 9.95 | 1 | 2024-02-01 | West | Glasscock |  |  | FALSE
Pauline BESS | Hunt Energy Network | 9.95 | 9.95 | 1 | 2024-02-01 | North | Henderson | 32.2515 | -95.9568 | FALSE
Mineral Wells East BESS | Hunt Energy Network | 9.95 | 9.95 | 1 | 2024-02-01 | North | Palo Pinto |  |  | FALSE